## Overview
Field | Value
Plan Title | Kaveri 3.0 — Marriage Registration & User Management Sprint Plan
Source | BRD_Requirements_Marriage_and_User_Management_v1.1.xlsx
Duration | 10 weeks (Sprint 1–10, 1 week each)
Team Size | 4 developers
Tech Stack | .NET Core (API/services) + Angular (citizen & officer UI)
Total Requirements | 410 (Marriage 299 + User Management 111)
Breakdown | FR 324 ¦ BR 50 ¦ NFR 36 (7 retired UM items excluded from active backlog)
Active Backlog Estimate | ~403 requirements; BRs implemented with paired FRs
Capacity Model | 4 devs × 5 days × 10 weeks = 200 person-days (~40 person-weeks)
Assumed Split | 2 Full-stack (Angular+.NET) ¦ 1 Backend-heavy (.NET/integrations) ¦ 1 Frontend-heavy (Angular/UX)
Sprint Cadence | 1-week sprints; demo + backlog refinement every Friday
Definition of Done | API + Angular UI + unit tests + RBAC wired + audit logged + bilingual where citizen-facing
Business Priority Logic | P0 Foundation (auth/RBAC) → P0 HMA Online end-to-end → P1 HMA Offline/Scan → P1 SMA → P2 PMA → P3 NFR/VAPT/hardening
Parallel Tracks | Track A: User Management platform ¦ Track B: Marriage Registration (HMA→SMA→PMA) sharing payment, eSign, eKYC, Scan, DSC
Velocity guidance
Target ~18–22 person-days of scoped work per sprint (buffer for spikes, code review, UAT fixes). Prefer completing vertical slices over partial horizontal layers. Shared platform (payment, eSign, eKYC, Scan, DSC) built once in HMA and reused by SMA/PMA.

## Sprint Plan
Sprint | Week | Business Priority | Theme / Goal | Track Focus | Dev Allocation (4) | Key Deliverables | Primary Requirement IDs (scope) | Exit Criteria / Demo | Est. Person-Days
1 | W1 | P0 | UM Foundation — Identity & Citizen Access | Track A primary; Track B spike | Dev1+Dev2: UM API/UI ¦ Dev3: OTP/SMS/Captcha adapters ¦ Dev4: Angular auth shell + citizen registration UX | Citizen self-registration with Aadhaar e-KYC; unique Username; dual OTP (mobile+email); Captcha; OTP login (no password); logout; session idle/absolute/single-session basics | FR-UM-001,004,008–011,062–064,069–076,085 ¦ NFR-UM-001–003,009–011 | Citizen can register, login via OTP, and land on secured shell; no password paths exist | 20
2 | W2 | P0 | UM Masters & Admin User Lifecycle | Track A | Dev1: Posts/Sanctioned/Office/Division masters API ¦ Dev2: Role Master + seed roles ¦ Dev3: Admin user create DSR/Other Dept ¦ Dev4: Admin Angular consoles | Office Hierarchy, Division, Posts, Sanctioned Posts, Post–Office-Type; Role Master seeds; create/edit/suspend/deactivate users; search/filter; SMS/email notifications on lifecycle | FR-UM-002,003,016,019–021,023–030,034–035,044,046–049,059,077,078 | Admin can create DSR & Other Dept users against sanctioned capacity; masters CRUD live | 20
3 | W3 | P0 | UM RBAC Runtime + Post Context | Track A MVP; Track B marriage shell | Dev1: Module/Function/Resource masters + RMF mapping ¦ Dev2: Runtime API/URL enforcement ¦ Dev3: Post selection + additional charge ¦ Dev4: Marriage service catalogue shell + channel UX | RBAC enforcement on APIs/URLs; DSR multi-post selection at login; additional charge of unoccupied subordinate posts; Application Admin seed actor; Marriage landing + channel choice skeleton | FR-UM-006,017,018,032,036–043,050–054 ¦ FR-HMA-046–050 (shell) | Role-gated APIs enforced; officer selects post and sees only permitted modules; Marriage channel screen wired to auth | 20
4 | W4 | P0 | UM Transfers/Absence + HMA Capture Core | Track A finish ops; Track B HMA data | Dev1: Transfer Out/In + occupancy midnight job ¦ Dev2: Temp absence / temp charge ¦ Dev3: HMA eligibility + party/witness/address APIs ¦ Dev4: HMA Angular multi-step forms | Relieving & joining; occupancy refresh job; temporary absence/charge; HMA eligibility (age, future date, marital status, jurisdiction); bride/groom/3 witnesses; e-Gov address MDM; SRO routing | FR-UM-057,058,060,066,068,079–084,087 ¦ FR-HMA-001–014,101,005–008 ¦ BR-HMA age/jurisdiction rules | Transfer & absence flows demoed; HMA draft application can be saved with statutory party data | 20
5 | W5 | P0 | HMA Online — Documents, eKYC, Forms, eSign | Track B primary; UM polish | Dev1: Document checklist + e-Janma/Marks Card ¦ Dev2: Aadhaar eKYC/Face Auth ¦ Dev3: Form I / Form IA PDF generation ¦ Dev4: eSign orchestration + Angular online flow | Configurable checklist; joint photo; eKYC reason OTP SMS; Form I & IA generation + statutory highlight panels; eSign by parties+witnesses; immutable artefacts; move to SR queue only after eSign | FR-HMA-015–019,091,102,053–058,083–087,089 ¦ BR-HMA form/eSign rules | Online HMA application reaches SR verification queue fully eSigned | 20
6 | W6 | P0 | HMA Online — SR Verify, Pay, Certificate | Track B — complete Online MVP | Dev1: SR workbench Online queue + approve/reject/refuse + DSC ¦ Dev2: Fee schedule + payment gateway + reconcile ¦ Dev3: Register entry + Form II-A + QR ¦ Dev4: Citizen payment/download Angular + notifications | SR single-stage online verification; defect/refuse orders; payment only after approval; receipt; block cert without reconcile; DSC gate; serial/volume register; Form II-A issue + download; integrity QR | FR-HMA-020–028,030,070,073,075–082,103,104 ¦ NFR-MRG-PAY-001 | End-to-end Online Hindu Marriage: apply → eSign → SR approve → pay → certificate download | 22
7 | W7 | P1 | HMA Offline + Shared Scanning Module | Track B Offline path | Dev1: Offline Stage 1 + appointment slots ¦ Dev2: Shared Scanning Module (AV, index, audit) ¦ Dev3: DEO allocation / Stage 2 / reassign ¦ Dev4: Printout QR pack + DEO Angular workbench | Stage 1 verify → pay+appointment single step → print Form I/IA/II-A → SR→DEO allocate → scan signed forms → Stage 2 → DSC/cert; Scanning Module reusable for SMA/PMA/Null-Void | FR-HMA-023,059–069,071–074,088,090 ¦ FR-SCAN-001–007 | Offline HMA completes at counter with DEO scan path; Scan module reusable | 22
8 | W8 | P1 | Special Marriage Act (SMA) — Notice to Certificate | Track B SMA; reuse platform | Dev1: Notice filing, 30-day residence/jurisdiction, publication ¦ Dev2: Objection window + solemnization scheduling ¦ Dev3: SMA forms/declarations/certificate + SR/DSC reuse ¦ Dev4: SMA Angular citizen+officer flows | Notice of intended marriage; statutory age/spouse rules; publication & objections; fresh notice if not solemnized in 3 months; both parties + 3 witnesses; Online/Offline reuse of pay/eSign/scan/DSC | FR-SMA-* (69 FRs) ¦ BR-SMA-001–014 ¦ reuse payment/eSign/scan/SR patterns | SMA notice→objection period→solemnization→certificate demo (Online happy path + Offline stub) | 22
9 | W9 | P2 | Parsi Marriage (PMA) + HMA Null & Void | Track B PMA + HMA back-office | Dev1: PMA eligibility, priest, Schedule II upload, 2 witnesses ¦ Dev2: PMA Online/Offline reuse of platform services ¦ Dev3: Null & Void endorsement + court order scan ¦ Dev4: PMA/Null-Void Angular + quarterly RG extract job | PMA Ashirvad registration (not solemnization); Schedule II priest certificate; prohibited degrees; Online/Offline; quarterly certified copy to Registrar-General; HMA Null/Void Sec.11/12 with register/certificate status | FR-PMA-001–058 ¦ BR-PMA-001–015 ¦ FR-HMA-094–099 | PMA E2E Online + Null & Void on registered HMA record | 20
10 | W10 | P3 | NFR Hardening, VAPT Closure, UM Remaining, UAT | Cross-cutting | Dev1: Perf/scale/availability ¦ Dev2: Security/privacy/audit/VAPT remediations ¦ Dev3: UM remaining (lost-mobile, mobile change, bilingual/GIGW) ¦ Dev4: UAT defect burn-down + reports/reprint polish | Marriage NFRs (PERF/SCALE/SEC/PRIV/AUD/AVA/PAY/VAPT); UM compliance & audit NFRs; Citizen lost-mobile FR-UM-056/065/086; bilingual EN/KN; GIGW; DR targets; concurrent session load; certificate reprint controls; UAT sign-off pack | NFR-MRG-* (12) ¦ NFR-UM-* remaining ¦ FR-UM-005,012,013,014,056,065,086 ¦ FR-HMA-031–033 | NFR checklist green; VAPT criticals closed; UAT exit criteria met for scoped MVP | 20

## Backlog by Module
Business Priority | Module / Area | Source | FR | BR | NFR | Active Scope Notes | Target Sprints
P0 | UM — Auth & Citizen | User Management | 25 | 0 | 8 | Registration, OTP login, sessions, eKYC at signup | S1
P0 | UM — Masters & Admin | User Management | 30 | 0 | 2 | Office/Posts/Roles/Sanctioned capacity, user CRUD | S2
P0 | UM — RBAC & Post Context | User Management | 18 | 0 | 2 | RMF mapping, API enforcement, post select, additional charge | S3
P0 | UM — Transfers & Absence | User Management | 15 | 0 | 2 | Transfer in/out, occupancy job, temp absence/charge | S4
P0 | HMA — Capture & Eligibility | Marriage | 35 | 10 | 0 | Channel, parties, witnesses, address MDM, jurisdiction | S4–S5
P0 | HMA — Online Forms & eSign | Marriage | 28 | 5 | 0 | Docs, eKYC, Form I/IA, eSign, SR queue entry | S5
P0 | HMA — Online Verify/Pay/Cert | Marriage | 25 | 4 | 1 | SR DSC, payment, Form II-A, register | S6
P1 | HMA — Offline + DEO | Marriage | 22 | 2 | 0 | Appointment, printout, DEO allocate, Stage 2 | S7
P1 | SCAN — Shared Scanning | Marriage | 7 | 0 | 0 | Multi-page scan, AV gate, index, audit | S7
P1 | SMA — Special Marriage | Marriage | 69 | 14 | 0 | Notice, objections, solemnization, certificate | S8
P2 | PMA — Parsi Marriage | Marriage | 58 | 15 | 0 | Schedule II, priest, 2 witnesses, quarterly RG | S9
P2 | HMA — Null & Void | Marriage | 6 | 0 | 0 | Court order endorsement, register/cert status | S9
P3 | Marriage NFRs / VAPT | Marriage | 0 | 0 | 12 | Perf, scale, security, privacy, audit, avail, pay, VAPT | S10
P3 | UM NFRs + residual FRs | User Management | 8 | 0 | 10 | Lost-mobile, profile, bilingual, GIGW, DR, audit retention | S10

## Team Board
Role | Developer | Primary Ownership | Secondary | Sprints Peak Load
Full-stack Lead | Dev1 | UM masters, transfers, Marriage SR/workflow, SMA notice APIs | Integrations coordination | S2–S4, S6–S8
Backend / Integrations | Dev2 | OTP/SMS, eKYC/Face Auth, payment, eSign, DSC, Scan AV, VAPT | NFR performance | S1, S5–S7, S10
Backend Services | Dev3 | RBAC runtime, occupancy jobs, Form PDF engines, PMA/Null-Void APIs | Fee schedule, registers | S3–S6, S9
Frontend Lead (Angular) | Dev4 | Citizen & officer Angular apps, bilingual UX, workbenches | GIGW accessibility | All sprints (UI of vertical slices)
Working agreements
1) Each story is a vertical slice (API + UI + audit + RBAC). 2) Shared platform stories (payment, eSign, eKYC, Scan, DSC) are built once in HMA and reused by SMA/PMA. 3) Retired UM IDs (FR-UM-015,023,031,055,061,067, NFR-UM-005) are out of scope. 4) Spike budget ≤10% per sprint. 5) Friday demo must show runnable citizen or officer path.

## Risks & Dependencies
ID | Type | Item | Impact | Mitigation | Needed By
D1 | Dependency | Aadhaar e-KYC / Face Auth sandbox & production credentials | High — blocks Citizen UM + Marriage Online | Secure credential request week 0; mock adapter until S1 mid-week | S1
D2 | Dependency | Payment gateway & fee schedule master data | High — blocks certificate issuance | Start fee master in S5; integrate gateway in S6 with retry/reconcile | S6
D3 | Dependency | eSign ASP / DSC token infrastructure for SRO | High — blocks Online completion & cert | Parallel procurement; stub signed-PDF store in S5 | S5–S6
D4 | Dependency | e-Janma & Marks Card APIs | Medium — age proof automation | Manual upload fallback always available (FR-HMA-102) | S5
D5 | Dependency | SMS gateway (OTP) + email SMTP | High — auth & notifications | Confirm rate limits & templates in S1 | S1
D6 | Dependency | MDM address (district/taluk/village) services | Medium — HMA-101 | Cache MDM locally; free-text not sole mode | S4
R1 | Risk | 410 reqs in 10 weeks is aggressive; SMA/PMA reuse assumed | High | Protect P0 Online HMA+UM MVP; defer PMA Offline edge cases if slip | Ongoing
R2 | Risk | SMA 30-day notice period hard to demo in sprint | Medium | Configurable shortened notice in non-prod for UAT | S8
R3 | Risk | VAPT late findings in S10 | High | Threat-model reviews in S3 & S6; security stories each sprint | S3,S6,S10
R4 | Risk | Scope creep from marriage FRS variants | Medium | Freeze sprint scope Monday; park changes to next sprint | Ongoing

## Milestones
Milestone | Week | Business Outcome | Success Metric
M1 — Secure Access Live | End W3 | Citizens & officers authenticate; RBAC gates modules | OTP login + role-denied API proof
M2 — HMA Online MVP | End W6 | Statutory Hindu Marriage registrable end-to-end online | Form II-A downloadable after pay+DSC
M3 — HMA Offline + Scan | End W7 | Counter channel operational with DEO scan | Stage 2 → certificate path
M4 — SMA Live | End W8 | Special Marriage notice-to-certificate capability | Notice published; certificate after solemnization
M5 — PMA + Null/Void | End W9 | Parsi registration + HMA nullity back-office | Schedule II path + void endorsement
M6 — Release Candidate | End W10 | NFR/VAPT/UAT exit for scoped release | Critical defects = 0; NFR checklist signed

## Coverage Summary
Source BRD | Type | Count | Planned Treatment
Marriage | FR | 237 | Implemented across S4–S9; HMA first, then SMA, then PMA
Marriage | BR | 50 | Encoded as validation rules with paired FRs (not separate stories)
Marriage | NFR | 12 | Hardening sprint S10 + continuous non-functional stories
User Management | FR | 87 | S1–S4 core; residual profile/recovery in S10 (~7 retired excluded)
User Management | NFR | 24 | Security/session with S1–S3; compliance/DR/audit in S10
Combined | Total | 410 | Business-priority sequenced; shared platform amortizes SMA/PMA