## Week 1 Overview
Field | Value
Sprint | 1
Week | W1
Business Priority | P0
Theme / Goal | UM Foundation — Identity & Citizen Access
Requirement Count | 25
Team | 4 Developers + 2 Testers
Capacity | 20 Dev person-days + 10 QA person-days
Tech Stack | .NET Core + Angular
Source Plan | Sprint_Plan_Requirement_IDs_Marriage_UM_10Weeks_v1.0.xlsx
Demo Goal (Fri) | Citizen can self-register (OTP email+mobile + eKYC stub) and Other Dept user can login with Captcha+OTP; session policies enforced
Exit Criteria | All 25 Req IDs implemented or NFR-verified; critical defects = 0; OTP & session policy unit+API tests green
Role Roster
Role | ID | Primary Ownership (W1) | Secondary
Full-stack Lead | Dev1 | User Master, Citizen registration orchestration, Username rules | API contracts for Angular
Backend / Integrations | Dev2 | OTP/SMS/Email service, Captcha, Aadhaar e-KYC adapter, OTP policy NFRs | Perf timings NFR-UM-009/010
Backend Services | Dev3 | Login APIs, Session/lockout, Logout, TLS & auth latency NFRs | Support Dev1 registration APIs
Frontend Lead (Angular) | Dev4 | Citizen registration UI, Login UI, Captcha/OTP screens, session UX | Bilingual-ready labels
QA — Registration & eKYC | QA1 | Citizen registration, dual OTP, eKYC, username uniqueness | Regression pack seed
QA — Auth & Session | QA2 | Login/OTP/Captcha, lockout, session idle/absolute/single-session, security NFRs | Perf smoke on OTP dispatch

## Requirement Ownership
Req ID | Type | Workstream | Primary Dev | Secondary Dev | Primary QA | Secondary QA | Dev Effort (pd) | QA Effort (pd) | Short Scope
FR-UM-001 | FR | Citizen Registration | Dev1 | Dev4 | QA1 | QA2 | 1.5 | 0.5 | Citizen self-registration orchestration (no approval)
FR-UM-004 | FR | User Master / Username | Dev1 | Dev3 | QA1 |  | 1 | 0.25 | Username unique across User Master; email/mobile not unique
FR-UM-062 | FR | User Master / Username | Dev1 | Dev4 | QA1 |  | 1 | 0.25 | Username derivation by category + admin-only correction hooks
FR-UM-063 | FR | Citizen Registration | Dev1 | Dev2 | QA1 |  | 1.5 | 0.75 | Dual contact OTP verify before account create
FR-UM-085 | FR | eKYC Integration | Dev2 | Dev1 | QA1 |  | 2 | 0.75 | Mandatory Aadhaar e-KYC (stub/sandbox) before account create
FR-UM-064 | FR | User Master / Username | Dev1 | Dev3 | QA1 | QA2 | 1 | 0.25 | DSR KGID unique; Other Dept DeptCode+EmpID + official email domain
FR-UM-007 | FR | Login / Auth | Dev3 | Dev4 | QA2 |  | 1 | 0.5 | Other Dept login: Username + Captcha + OTP (no biometric)
FR-UM-008 | FR | Session | Dev3 | Dev4 | QA2 |  | 0.5 | 0.25 | Logout terminates active session
FR-UM-009 | FR | Login / Auth | Dev3 | Dev1 | QA2 |  | 0.5 | 0.25 | No password login/reset/change for any category
FR-UM-010 | FR | OTP Platform | Dev2 | Dev3 | QA2 | QA1 | 1 | 0.5 | Login OTP SMS-only to registered mobile ≤5s
FR-UM-011 | FR | Login / Auth | Dev2 | Dev4 | QA2 |  | 0.75 | 0.5 | Captcha validated before OTP dispatch (all categories)
FR-UM-069 | FR | OTP Platform | Dev2 | Dev3 | QA2 |  | 0.5 | 0.25 | OTP validity: login 5m; reg/reset 10m (IST)
FR-UM-070 | FR | OTP Platform | Dev2 |  | QA2 |  | 0.25 | 0.15 | OTP/PIN = 6 numeric digits
FR-UM-071 | FR | OTP Platform | Dev2 | Dev3 | QA2 |  | 0.5 | 0.25 | Max 3 incorrect entries per OTP then invalidate
FR-UM-072 | FR | OTP Platform | Dev2 |  | QA2 |  | 0.5 | 0.25 | 60s resend cooldown; max 3 resends / 15 min / channel
FR-UM-073 | FR | Session / Lockout | Dev3 | Dev2 | QA2 |  | 0.75 | 0.5 | 5 failed logins → 15m Username lockout (+ admin unlock hook)
FR-UM-074 | FR | Session | Dev3 | Dev4 | QA2 |  | 0.75 | 0.5 | Idle timeout 10 minutes
FR-UM-075 | FR | Session | Dev3 | Dev4 | QA2 |  | 0.5 | 0.25 | Absolute session max 4 hours
FR-UM-076 | FR | Session | Dev3 | Dev4 | QA2 |  | 0.75 | 0.5 | Single active session per Username (last-login-wins)
NFR-UM-001 | NFR | Security | Dev3 | Dev1 | QA2 |  | 0.25 | 0.25 | No password storage; OTP-only auth
NFR-UM-002 | NFR | Security | Dev2 | Dev3 | QA2 |  | 0.5 | 0.5 | OTP+session policy conformance (maps FR-UM-069–076)
NFR-UM-003 | NFR | Security | Dev3 |  | QA2 |  | 0.5 | 0.25 | TLS 1.2+ for all data in transit
NFR-UM-009 | NFR | Performance | Dev2 |  | QA2 |  | 0.25 | 0.25 | Login OTP SMS dispatch ≤5s
NFR-UM-010 | NFR | Performance | Dev2 |  | QA1 |  | 0.25 | 0.25 | Reg OTP email/mobile dispatch ≤30s
NFR-UM-011 | NFR | Performance | Dev3 |  | QA2 |  | 0.25 | 0.25 | Auth complete ≤2s after OTP verify
Dev effort total (pd) | [6 empty] | 18.25
QA effort total (pd) | [7 empty] | 9.15

## Developer Day Plan
Day | Dev | Role | Focus Tasks (granular) | Req IDs | Deliverable / DoD | Depends On
Mon | Dev1 | Full-stack Lead | DB: User Master schema (Username PK/unique, category, mobile, email, KGID, DeptCode, EmpID, status); Username availability API; OpenAPI contracts for registration & login | FR-UM-004, FR-UM-062, FR-UM-064 | Migration + User entity + uniqueness indexes + Swagger stubs | None
Mon | Dev2 | Backend / Integrations | OTP core service: 6-digit generator, IST expiry (5m/10m), store hashed OTP, single-use invalidate; SMS gateway client (login OTP); email OTP client (registration) | FR-UM-069, FR-UM-070, FR-UM-010, FR-UM-063 | OtpService + SMS/Email adapters (sandbox) unit-tested | None
Mon | Dev3 | Backend Services | Auth module skeleton: JWT/session store; no-password enforcement; logout endpoint; TLS config checklist | FR-UM-008, FR-UM-009, NFR-UM-001, NFR-UM-003 | Auth project + logout + password endpoints removed/blocked | Dev1 User Master
Mon | Dev4 | Frontend Lead | Angular UM module scaffold: routes for Register / Login / OTP Verify; shared Captcha + OTP input components; form validators | FR-UM-001, FR-UM-007, FR-UM-011 | Shell screens with reactive forms + API service stubs | None
Tue | Dev1 | Full-stack Lead | Citizen registration API: create draft → verify email OTP → verify mobile OTP → require eKYC success → commit account (instant, no approval) | FR-UM-001, FR-UM-063, FR-UM-085 | POST /citizens/register + verify endpoints green in Postman | Dev2 OTP, Dev2 eKYC stub
Tue | Dev2 | Backend / Integrations | Captcha service + validate-before-OTP gate; resend cooldown 60s & max 3/15m; max 3 wrong entries; Aadhaar e-KYC adapter (sandbox/stub) with consent+audit log | FR-UM-011, FR-UM-071, FR-UM-072, FR-UM-085, NFR-UM-002 | Captcha+OTP policy APIs; eKYC Initiate/Verify stub | None
Tue | Dev3 | Backend Services | Other Dept login API: Username + Captcha + OTP; lockout after 5 fails (15m); wire OTP dispatch SMS-only | FR-UM-007, FR-UM-010, FR-UM-073 | POST /auth/login/request-otp + /auth/login/verify | Dev2 OTP/Captcha, Dev1 User Master
Tue | Dev4 | Frontend Lead | Citizen registration wizard UI: Username availability check, email/mobile, dual OTP screens, eKYC step placeholder | FR-UM-001, FR-UM-062, FR-UM-063, FR-UM-085 | End-to-end UI wired to Dev1 APIs (happy path) | Dev1 APIs
Wed | Dev1 | Full-stack Lead | Other Dept / DSR validation rules API (KGID unique; DeptCode+EmpID uniqueness; official email domain list); admin Username correction audit stub | FR-UM-064, FR-UM-062 | Validation endpoints + domain allowlist config | None
Wed | Dev2 | Backend / Integrations | Perf instrumentation: OTP SMS ≤5s, reg OTP ≤30s; harden hashing/rate-limit; audit logging for OTP events | NFR-UM-009, NFR-UM-010, NFR-UM-002 | Metrics + unit/integration timing asserts | Tue OTP
Wed | Dev3 | Backend Services | Session policies: idle 10m, absolute 4h, single session last-login-wins + prior-session invalidate message; auth latency ≤2s | FR-UM-074, FR-UM-075, FR-UM-076, NFR-UM-011 | Session middleware + Redis/DB session store | Tue login
Wed | Dev4 | Frontend Lead | Other Dept login UI + Captcha + OTP entry; logout; idle/absolute timeout warnings; single-session kick message | FR-UM-007, FR-UM-008, FR-UM-011, FR-UM-074, FR-UM-075, FR-UM-076 | Login E2E UI against Dev3 APIs | Dev3 APIs
Thu | Dev1 | Full-stack Lead | Bugfix from QA1; edge cases (duplicate Username, incomplete eKYC blocks create, email/mobile non-unique allowed) | FR-UM-001, FR-UM-004, FR-UM-063 | Critical/High defects closed for registration | QA1 findings
Thu | Dev2 | Backend / Integrations | Bugfix OTP/Captcha/eKYC; resend & expiry edge cases; SMS channel never used for email OTP | FR-UM-010, FR-UM-069–072, FR-UM-085 | OTP/eKYC defects closed; channel separation verified | QA1/QA2
Thu | Dev3 | Backend Services | Bugfix login/session/lockout; admin unlock-with-reason hook for FR-UM-073; TLS verify in all environments | FR-UM-007, FR-UM-073–076, NFR-UM-003 | Auth/session defects closed | QA2
Thu | Dev4 | Frontend Lead | UX polish: error messages for lockout/cooldown/expiry; disable password fields; accessibility basics on forms | FR-UM-009, FR-UM-071–074 | UI ready for Fri demo | QA findings
Fri | Dev1 | Full-stack Lead | Demo prep: seed Other Dept user; walkthrough registration; stabilize APIs; sprint burndown update | FR-UM-001, FR-UM-004, FR-UM-062–064 | Demo script + seed data | All
Fri | Dev2 | Backend / Integrations | Demo: live OTP SMS/email (sandbox) + eKYC stub success/fail paths; NFR timing evidence snapshot | FR-UM-085, NFR-UM-009, NFR-UM-010 | Timing evidence sheet for NFRs | All
Fri | Dev3 | Backend Services | Demo: Other Dept login + lockout + idle timeout + second-login kicks first; NFR-UM-011 evidence | FR-UM-007, FR-UM-073–076, NFR-UM-011 | Auth demo path stable | All
Fri | Dev4 | Frontend Lead | Fri demo UI polish; capture screenshots; fix P0 UI bugs only | All UI Req IDs | Runnable citizen + officer/Other Dept path | All

## Tester Day Plan
Day | Tester | Focus | Test Activities (granular) | Req IDs Under Test | Test Artifacts | Entry Criteria
Mon | QA1 | Test Design — Registration | Write test cases: Citizen registration happy path; Username uniqueness; email/mobile non-uniqueness; dual OTP order; eKYC mandatory; incomplete verification blocks create; no security questions | FR-UM-001, FR-UM-004, FR-UM-062, FR-UM-063, FR-UM-085 | TC pack REG-01..REG-25 in test mgmt | BRD + Sprint 1 sheet
Mon | QA2 | Test Design — Auth/Session | Write test cases: Other Dept login Captcha+OTP; no password paths; OTP SMS-only; validity/expiry; 3 wrong entries; resend cooldown; lockout 15m; idle 10m; absolute 4h; single session; logout; TLS check list | FR-UM-007–011, FR-UM-069–076, NFR-UM-001–003, NFR-UM-009–011 | TC pack AUTH-01..AUTH-40 | BRD + Sprint 1 sheet
Tue | QA1 | Env + Data Prep | Prepare test mobiles/emails; Username collision dataset; official email domain allowlist samples; eKYC success/fail fixtures; Postman collection for registration APIs | FR-UM-001, FR-UM-063, FR-UM-064, FR-UM-085 | Test data sheet + Postman REG collection | Dev1/Dev2 APIs partially ready
Tue | QA2 | Env + Data Prep | Other Dept seed users; Captcha test keys; SMS sandbox inbox; lockout/session timing harness; Postman AUTH collection; perf stopwatch for OTP dispatch | FR-UM-007, FR-UM-010, FR-UM-011, NFR-UM-009–011 | Test data + Postman AUTH + timing sheet | Dev2/Dev3 APIs partially ready
Wed | QA1 | Execute — Registration API | Execute REG pack on APIs: create, dual OTP, eKYC gate, duplicate Username reject, shared mobile allowed, account not created if eKYC fails; log defects | FR-UM-001, FR-UM-004, FR-UM-062, FR-UM-063, FR-UM-085, NFR-UM-010 | Executed TC + defects filed | Dev1 registration APIs merge
Wed | QA2 | Execute — Login/OTP API | Execute AUTH pack on APIs: Captcha gate, OTP SMS channel, expiry, resend limits, 3-fail invalidate, 5-fail lockout, logout; start session policy tests | FR-UM-007–011, FR-UM-069–073, NFR-UM-001, NFR-UM-002, NFR-UM-009 | Executed TC + defects filed | Dev3 login APIs merge
Thu | QA1 | Execute — UI Registration + Retest | UI E2E Citizen registration wizard; accessibility smoke; retest Dev1/Dev2 fixes; FR-UM-064 validation (KGID / Dept email domain) negative tests | FR-UM-001, FR-UM-062–064, FR-UM-085 | UI E2E results + retest log | Dev4 UI + defect fixes
Thu | QA2 | Execute — Session UI + NFR | UI login/logout; idle timeout warning; absolute 4h (accelerated clock if available); single-session kick; TLS 1.2+ check; auth ≤2s after OTP; NFR-UM-002 matrix sign-off | FR-UM-008, FR-UM-074–076, NFR-UM-002, NFR-UM-003, NFR-UM-011 | Session/NFR evidence + defects | Dev3 session + Dev4 UI
Fri | QA1 | Regression + Demo Support | Sanity regression REG pack; support Fri demo; sign-off Citizen registration exit criteria; list carry-over (if any) | All QA1 Req IDs | W1 QA1 exit report | Critical defects fixed
Fri | QA2 | Regression + Demo Support | Sanity regression AUTH/Session pack; OTP timing evidence attached; support Fri demo Other Dept login; W1 exit sign-off | All QA2 Req IDs | W1 QA2 exit report + NFR evidence | Critical defects fixed

## Daily Board Mon-Fri
Day | Dev1 | Dev2 | Dev3 | Dev4 | QA1 | QA2 | Integration Checkpoint
Mon | User Master + contracts | OTP+SMS+Email core | Auth skeleton + logout + TLS | Angular UM scaffold | REG test design | AUTH test design | Agree API contracts (OpenAPI)
Tue | Citizen register APIs | Captcha + OTP policy + eKYC stub | Other Dept login + lockout | Registration wizard UI | Test data + Postman REG | Test data + Postman AUTH | Registration happy-path API dry-run
Wed | Dept/DSR validation rules | OTP perf + audit harden | Session idle/4h/single | Login + session UX | Execute REG APIs | Execute AUTH APIs | Login E2E API+UI smoke
Thu | Registration bugfix | OTP/eKYC bugfix | Session/lockout bugfix | UI polish + a11y | UI E2E + retest | Session/NFR execute | Defect triage (P0/P1 only)
Fri | Demo + seed data | NFR timing evidence | Auth demo path | Demo UI polish | REG exit sign-off | AUTH exit sign-off | Fri demo: Citizen register + Other Dept login

## Capacity & Exit
Person | Mon | Tue | Wed | Thu | Fri | Total (pd) | Notes
Dev1 | 1 | 1 | 1 | 1 | 1 | 5 | Registration + User Master
Dev2 | 1 | 1 | 1 | 1 | 1 | 5 | OTP/eKYC/Captcha (S1 peak)
Dev3 | 1 | 1 | 1 | 1 | 1 | 5 | Login + Session
Dev4 | 1 | 1 | 1 | 1 | 1 | 5 | Angular UI
QA1 | 1 | 1 | 1 | 1 | 1 | 5 | Registration & eKYC
QA2 | 1 | 1 | 1 | 1 | 1 | 5 | Auth & Session
Week 1 Exit Criteria
1. Citizen self-registration works end-to-end with dual OTP + eKYC stub (FR-UM-001, 063, 085).
2. Username uniqueness enforced; email/mobile may duplicate (FR-UM-004, 062).
3. Other Department login works with Captcha + OTP SMS-only; no password UI/API (FR-UM-007, 009–011).
4. OTP policy FR-UM-069–072 and lockout FR-UM-073 verified by QA2.
5. Session idle 10m, absolute 4h, single-session, logout verified (FR-UM-008, 074–076).
6. NFR-UM-001–003 and NFR-UM-009–011 evidenced (timing sheet + TLS check).
7. Zero open Critical defects; High defects have owners for Week 2.
8. Friday demo completed with runnable Citizen + Other Dept paths.
Carry-forward note
DSR face/biometric login is NOT in Week 1 (Other Dept OTP only). Full admin user lifecycle & masters start Week 2. Lost-mobile reset (FR-UM-056) is later.