## Document Registration
Document Registration Module - Effort Estimation (in Days)
S.No | Module / Task | Effort (Days)
1 | Stamp Duty Calculator | 9
i | API | 3
ii | UI | 2
iii | Code Review (CR) | 2
iv | Testing (T) | 2
2 | Fee Calculator (Registration fee & others) | 5
i | API | 2
ii | UI | 1
iii | Code Review (CR) | 1
iv | Testing (T) | 1
3 | Receipt Creation | 3
i | API | 1
ii | UI | 1
iii | Code Review (CR) | 0.5
iv | Testing (T) | 0.5
4 | Property Valuation | 10
i | API | 3
ii | UI | 3
iii | Code Review (CR) | 2
iv | Testing (T) | 2
5 | Property Valuation Communication Slip | 3
i | API | 1
ii | UI | 1
iii | Code Review (CR) | 0.5
iv | Testing (T) | 0.5
6 | Court Order Data Entry (22B Entries) | 6
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 1
iv | Testing (T) | 1
7 | Exemptions Data Entry | 6
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 1
iv | Testing (T) | 1
8 | Home Page Design | 8
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 2
iv | Testing (T) | 2
9 | Home EODB Dashboard | 8
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 2
iv | Testing (T) | 2
10 | Property Add / Modify / Delete | 7
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 2
iv | Testing (T) | 1
11 | Legal Hold Liabilities Display | 2
i | API | 0.5
ii | UI | 0.5
iii | Code Review (CR) | 0.5
iv | Testing (T) | 0.5
12 | Party CRUD | 8
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 2
iv | Testing (T) | 2
13 | Witness CRUD | 8
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 2
iv | Testing (T) | 2
14 | Party e-KYC Integration | 8
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 2
iv | Testing (T) | 2
15 | Property Integration (e-Swathu, Bhoomi, BDA, KHB, Mojini) | 45
i | API | 15
ii | UI | 15
iii | Code Review (CR) | 5
iv | Testing (T) | 10
16 | Capture Photo, Biometric | 8
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 2
iv | Testing (T) | 2
17 | Integration with PAN | 8
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 2
iv | Testing (T) | 2
18 | Integration with Passport | 8
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 2
iv | Testing (T) | 2
19 | Fee Calculation Screen | 8
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 2
iv | Testing (T) | 2
20 | SRO Scrutiny Page | 8
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 2
iv | Testing (T) | 2
21 | Document Presentation Page | 8
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 2
iv | Testing (T) | 2
22 | Photo & Thumb Capture Screen - DEO (Add New Identifiers) | 8
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 2
iv | Testing (T) | 2
23 | Generate Endorsement | 9
i | API | 3
ii | UI | 2
iii | Code Review (CR) | 2
iv | Testing (T) | 2
24 | Registration Screen | 10
i | API | 4
ii | UI | 2
iii | Code Review (CR) | 2
iv | Testing (T) | 2
25 | DSC Sign & Integration | 12
i | API | 3
ii | UI | 3
iii | Code Review (CR) | 3
iv | Testing (T) | 3
26 | Digital e-Stamp Template Design | 8
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 2
iv | Testing (T) | 2
27 | Integration with Payment Gateway | 8
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 2
iv | Testing (T) | 2
28 | Integration with KSRAC | 10
i | API | 3
ii | UI | 3
iii | Code Review (CR) | 2
iv | Testing (T) | 2
29 | Implementing Undervaluation Flow / Impounding Flow | 16
i | API | 5
ii | UI | 5
iii | Code Review (CR) | 3
iv | Testing (T) | 3
30 | Verifying Document | 4
i | API | 1
ii | UI | 1
iii | Code Review (CR) | 1
iv | Testing (T) | 1
31 | Fruits APIs | 27
i | API | 15
ii | UI | 5
iii | Code Review (CR) | 2
iv | Testing (T) | 5
32 | Rule 17(2), 17(3), 17(1) Filings | 30
i | API | 10
ii | UI | 10
iii | Code Review (CR) | 5
iv | Testing (T) | 5
33 | Scanning Module Integration | 14
i | API | 5
ii | UI | 5
iii | Code Review (CR) | 2
iv | Testing (T) | 2
34 | Cross Reference Module | 8
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 2
iv | Testing (T) | 2
35 | Re-Registration | 14
i | API | 5
ii | UI | 5
iii | Code Review (CR) | 2
iv | Testing (T) | 2
36 | Will After Death of Testator | 14
i | API | 5
ii | UI | 5
iii | Code Review (CR) | 2
iv | Testing (T) | 2
37 | Verify Power of Attorney Document | 8
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 2
iv | Testing (T) | 2
38 | Generate Income Tax SFT Report | 14
i | API | 5
ii | UI | 5
iii | Code Review (CR) | 2
iv | Testing (T) | 2
39 | Search Form for Investigation Department | 10
i | API | 3
ii | UI | 3
iii | Code Review (CR) | 2
iv | Testing (T) | 2
40 | Valuation Form I Creation & Submission | 8
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 2
iv | Testing (T) | 2
41 | Deposit of Will (Closed Will) | 30
i | API | 10
ii | UI | 10
iii | Code Review (CR) | 5
iv | Testing (T) | 5
42 | SRO Dashboard (Login) | 20
i | API | 5
ii | UI | 5
iii | Code Review (CR) | 5
iv | Testing (T) | 5
43 | Workflow Implementation - Document Registration | 30
i | API | 10
ii | UI | 10
iii | Code Review (CR) | 5
iv | Testing (T) | 5
44 | Refund Module | 30
i | API | 10
ii | UI | 10
iii | Code Review (CR) | 5
iv | Testing (T) | 5
45 | Correction Module (Misc G8(2)) | 50
i | API | 15
ii | UI | 15
iii | Code Review (CR) | 10
iv | Testing (T) | 10
46 | XML/JSLIP Push to Other Department | 22
i | API | 10
ii | UI | 2
iii | Code Review (CR) | 5
iv | Testing (T) | 5
47 | SMS/Email Integration | 4
i | API | 1
ii | UI | 1
iii | Code Review (CR) | 1
iv | Testing (T) | 1
48 | e-Sign Integration | 4
i | API | 1
ii | UI | 1
iii | Code Review (CR) | 1
iv | Testing (T) | 1
49 | Digilocker Integration | 30
i | API | 10
ii | UI | 10
iii | Code Review (CR) | 5
iv | Testing (T) | 5
50 | Daily Register | 14
i | API | 5
ii | UI | 5
iii | Code Review (CR) | 2
iv | Testing (T) | 2
51 | MIS Reports (All Post-Registration Reports) | 25
i | API | 10
ii | UI | 5
iii | Code Review (CR) | 5
iv | Testing (T) | 5
52 | Integration with GIS | 27
i | API | 10
ii | UI | 5
iii | Code Review (CR) | 7
iv | Testing (T) | 5
53 | Integration with Scality | 14
i | API | 5
ii | UI | 2
iii | Code Review (CR) | 5
iv | Testing (T) | 2
54 | IGR Appeal Cases Related to Undervaluation | 14
i | API | 5
ii | UI | 5
iii | Code Review (CR) | 2
iv | Testing (T) | 2
55 | CVC Valuation Data Entry Module | 30
i | API | 10
ii | UI | 10
iii | Code Review (CR) | 5
iv | Testing (T) | 5
56 | Minute Book Entry | 11
i | API | 5
ii | UI | 2
iii | Code Review (CR) | 2
iv | Testing (T) | 2
57 | Old Pending Document Registration (Pre Kaveri/Kaveri 1 and Kaveri 2) | 30
i | API | 10
ii | UI | 10
iii | Code Review (CR) | 5
iv | Testing (T) | 5

## Summary
Effort Summary by Category
Category | Total Effort (Days)
API | 264.5
UI | 225.5
Code Review (CR) | 154.5
Testing (T) | 156.5
TOTAL | 801

## Notes
Legend
i - API | Application Programming Interface development effort (in days)
ii - UI | User Interface development effort (in days)
iii - Code Review (CR) | Code Review effort (in days)
iv - Testing (T) | Testing effort (in days)
Effort (Days) on task row | Sum of API + UI + Code Review + Testing for that task
Note: | Rows highlighted in red italic text in the Notes column have handwriting in the source notes that was unclear or partly obscured. Please verify: Item 9 (module name), Item 31 (task name), Item 53 (UI value).