## Sheet1
ID | Task Name | Resource(s) | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10
1 | Design | PO, BA, UI/UX | bar: W1
1.1 | Functional Scope & Workflow | PO, BA | bar: W1
1.2 | UI/UX Wireframes & Flows | UI/UX | bar: W1 to W2
2 | Technical Foundation | Arch, DBA, DevOps | bar: W3 to W4
2.1 | Arch Design & Patterns | Architect | bar: W3 to W4
2.2 | DB Schema & Environment | DBA, DevOps | bar: W4 to W5
3 | Integration & Contracts | Int. Eng | bar: W3
3.1 | API Contracts & Swagger | Int. Eng | bar: W3
4 | Core Service Dev | Devs (10) | bar: W5 to W6
4.1 | Auth, SMS, Payment, e-Sign | Devs | bar: W5 to W6
4.2 | Aadhaar, DigiLocker | Devs | bar: W5 to W6
5 | Module Implementation | Devs (10) | bar: W5 to W7
5.1 | Marriage Registration | Devs | bar: W5 to W7
6 | Testing & Hardening | Testers, QA | bar: W5 to W8
6.1 | Test Scenarios & Execution | Testers | bar: W5 to W8
6.2 | Security Audit & QA Cert | QA | bar: W9
7 | Closure | PO, PM | bar: W10

## Sheet2
ID | Task Name | Resource(s) | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
1 | Discovery & Design | PO, BA, UI/UX | bar: W1 to W2
1.1 | Functional Scope & Workflow | PO, BA | bar: W1 to W2
1.2 | UI/UX Wireframes & Flows | UI/UX | bar: W2 to W3
2 | Technical Foundation | Arch, DBA, DevOps | bar: W2 to W3
2.1 | Arch Design & Patterns | Architect | bar: W2 to W3
2.2 | DB Schema & Environment | DBA, DevOps | bar: W3 to W4
3 | Integration & Contracts | Int. Eng | bar: W3 to W4
3.1 | API Contracts & Swagger | Int. Eng | bar: W3 to W4
4 | Core Service Dev | Devs (10) | bar: W4 to W7
4.1 | Auth, SMS, Payment, e-Sign | Devs | bar: W4 to W7
4.2 | Aadhaar, DigiLocker | Devs | bar: W5 to W7
5 | Module Implementation | Devs (10) | bar: W6 to W10
5.1 | Marriage Registration Logic | Devs | bar: W6 to W10
5.2 | Blazor UI Development | Devs | bar: W7 to W10
6 | Testing & Hardening | Testers, QA | bar: W8 to W11
6.1 | Test Scenarios & Execution | Testers | bar: W8 to W11
6.2 | Security Audit & QA Cert | QA | bar: W11 to W12
7 | Closure & Sign-off | PO, PM | bar: W12