# Project Objective

The objective is to develop a completely new software suite for Kaveri 3.0 that is architecturally scalable, highly secure, and delivers a better User Experience (UI/UX).

# Envisaged Modules

The following core modules are planned for the complete Kaveri 3.0 ecosystem:

- Document Registration

- Market Valuation

- Stamp Duty (SD) & Registration Fee (RF) Estimation

- Marriage Registration

- Firm Registration

- Encumbrance Search

- Certified Copies

# MVP (Minimal Viable Product) Strategy & Foundational Architecture

To initiate development, the Marriage Registration module will be executed first as the Minimum Viable Product (MVP). This approach allows the Kaveri IT team to build, test, and freeze the underlying system and technical architecture before scaling up to more complex/other modules.

Concurrently, the team will develop the core common microservices required to support Marriage Registration and all subsequent modules:

- User Management (including Transfers and Taking Charge workflows)

- SMS Gateway Integration

- e-Payment Gateway

- Accounting Ledger

- e-Sign and Digital Signature Certificate (DSC) Infrastructure

- Aadhaar e-KYC Integration

- MIS Reports & Daily Receipt Generation

- DigiLocker Integration

# Immediate Resource Requirements for MVP

To successfully deliver the Marriage Registration MVP and the foundational microservices, a hybrid team structure of existing domain/technical experts and new technical hires is required. This ensures continuity of business knowledge while incorporating modern architectural capabilities into the project..

# Existing resources

The following resources are already engaged with the Kaveri project. Their considerable experience with the department's existing operations, domain rules, and technology will be leveraged to guide the MVP requirements.

| Sr.No | Resource Type | Count | Key Activities, Tasks & Responsibilities |
| --- | --- | --- | --- |
|  | Product Owner | 1 | Defining boundaries for core services and the marriage module, ensuring functional requirements translate to system features, and managing final acceptances, approvals, and sign-offs. |
|  | Project Manager | 1 | Managing developer tasks, maintaining Gantt charts, and generating weekly status reports. |
|  | Business Analyst | 1 | Translating Kaveri 2.0 workflows to Kaveri 3.0, documenting validation logic, and ensuring all features are fully developed. |
|  | Database Administrator | 1 | Handling database creation, programming requirements, and ongoing administration activities. |
|  | Total | 4 |  |

# New resources via recruitment

| Sr.No | Resource Type | Count | Key Activities, Tasks & Responsibilities |
| --- | --- | --- | --- |
|  | Technical Architect | 1 | Outlining microservices architecture, selecting libraries and RDBMS, defining routing rules, enforcing Clean Architecture, and ensuring security and compliance. |
|  | Full Stack Developer | 4 | Executing software development tasks as assigned by the Project Manager. |
|  | Test Engineers | 2 | Writing end-to-end test scenarios for marriage registration, creating automation scripts, and conducting manual testing. |
|  | DevOps & Release Manager | 1 | Managing Dockerfiles and Docker Compose configurations, automating CI/CD pipelines, and documenting deployment, monitoring, and rollback procedures for staging and production. |
|  | Total | 8 |  |

# Gantt chart

| ID | Task Name | Resource(s) | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Design | PO, BA, UI/UX | X |  |  |  |  |  |  |  |  |  |
| 1.1 | Functional Scope & Workflow | PO, BA | X |  |  |  |  |  |  |  |  |  |
| 1.2 | UI/UX Wireframes & Flows | BA | X | X |  |  |  |  |  |  |  |  |
| 2 | Technical Foundation | Arch, DBA, DevOps |  |  | X | X |  |  |  |  |  |  |
| 2.1 | Arch Design & Patterns | Architect |  |  | X | X |  |  |  |  |  |  |
| 2.2 | DB Schema & Environment | DBA, DevOps |  |  |  | X | X |  |  |  |  |  |
| 3 | Integration & Contracts | Devs |  |  | X |  |  |  |  |  |  |  |
| 3.1 | API Contracts & Swagger | Devs |  |  | X |  |  |  |  |  |  |  |
| 4 | Core Service Dev | Devs |  |  |  |  | X | X |  |  |  |  |
| 4.1 | Auth, SMS, Payment, e-Sign | Devs |  |  |  |  | X | X |  |  |  |  |
| 4.2 | Aadhaar, DigiLocker | Devs |  |  |  |  | X | X |  |  |  |  |
| 5 | Module Implementation | Devs |  |  |  |  | X | X | X |  |  |  |
| 5.1 | Marriage Registration | Devs |  |  |  |  | X | X | X |  |  |  |
| 6 | Testing | Testers |  |  |  |  | X | X | X | X |  |  |
| 6.1 | Test Scenarios & Execution | Testers |  |  |  |  | X | X | X | X |  |  |
| 6.2 | Security Audit & QA Cert |  |  |  |  |  |  |  |  |  | X |  |
| 7 | Closure | PO, PM |  |  |  |  |  |  |  |  |  | X |