## Plan
Sl No | Phase | Workstream | Activity / Task | Expected Output / Evidence | Dependency | Priority | Owner / SME | Status | Target Date | Remarks | Comments | Comments By | CSG Role | Kaveri IT Cell | Commnets | Start Date | End Date
1 | Phase 1 | Application Discovery | Identify all Kaveri application modules and business functions. | Application/module inventory | Column1 | High | Column2 | Not Started | Column3 | Completed |  |  | Completed |  | 1. Document Registration 2. Marriage Registration 3. Firm Registration 4. Society Registration 5. Market Value Estimation 6. Stamp Duty Calculation 7. Registration Fee Calculation 8. Section 68 module 9. Liability Entry module 10. Scanning module 11. DSC Signing module 12. Encumbrance Certificate 13. Certified Copy 14. Accounting Module 15. Appointment Scheduling 16. User Management 17. Court Order Management 18. Workflow Management 19. Notification Services 20. Reporting & MIS 21. Paperless Registration, | TBD | TBD
2 | Phase 1 | Application Discovery | Conduct application walk-through for citizen, sub-registrar, admin, reporting and support flows. | Walkthrough notes and demo recordings |  | High |  | Not Started |  | Support of AI Tool like copilot will be helpful | 1. Document Registration 2. Marriage Registration 3. Firm Registration 4. Society Registration 5. Market Value Estimation 6. Stamp Duty Calculation 7. Registration Fee Calculation 8. Section 68 module 9. Liability Entry module 10. Scanning module 11. DSC Signing module 12. Encumbrance Certificate 13. Certified Copy 14. Accounting Module 15. Appointment Scheduling 16. User Management 17. Court Order Management 18. Workflow Management 19. Notification Services 20. Reporting & MIS 21. Paperless Registration, | added module list, mvprash | KT Co-ordinator, BA | Full Stack Developers, BA, PM, PO, Transition manager, Technical architect
3 | Phase 1 | Source Code | Identify source code repositories for UI, APIs, services, scripts, reports and database scripts. | Repository inventory with URLs |  | High |  | Not Started |  |  | Know -> Purpose of the code, Build process, dependencies, Branch structure and deployment processes | mvprash | KT Co-ordinator, DevOps | DevOps, PM, PO, Transition manager
4 | Phase 1 | Source Code | Obtain read access to source repositories and validate access with sample checkout. | Access confirmation and sample checkout evidence | Access approval | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Development Lead, DevOps | Full Stack Developers, DevOps, PM, PO, Transition manager
5 | Phase 1 | Environment | Identify Dev, SIT, Pre-Prod, Prod, environments. | Environment inventory |  | High |  | Not Started |  |  | add staging | mvprash | KT Co-ordinator, Development Lead Technical Architect, DevOps | Full Stack Developers, DevOps, PM, PO, Transition manager
6 | Phase 1 | Environment | Share environment URLs, login process, VPN/VDI/bastion requirements and access approvers. | Environment access matrix |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Technical Architect, DevOps | Technical Architect, Technology Lead, BA DevOps, PM, PO, Transition manager
7 | Phase 1 | Access Readiness | Provide access for application, source code, DevOps, DB, infra, monitoring, logs and file/object store. | Access tracker | Approver list | High |  | Not Started |  |  | as read-only, provide git hub accounts/credentials | mvprash | KT Co-ordinator, Technical Architect, DevOps, KPMU (PM), SDC Team | Technical Architect, Technology Lead, BA DevOps, PM, PO, Transition manager, DBA
8 | Phase 2 | Infrastructure Readiness | Review current hosting model: data center, VM, container, DockerDesktop or mixed. Share the application and infrastructure topology | Infrastructure topology |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Technical Architect, DevOps, KPMU (PM), SDC Team | Technical Architect, Technology Lead, BA DevOps, PM, PO, Transition manager, QA
9 | Phase 2 | Infrastructure Readiness | Share server inventory, resource allocation, OS/runtime versions and ownership. | Server inventory |  | High |  | Not Started |  |  | All prod server inventories, the purpose, deployment procedures, UAT procedures, release processes, DR operations (if any) | mvprash | KT Co-ordinator, Technical Architect, DevOps, KPMU (PM), SDC Team | Technical Architect, Technology Lead, BA DevOps, PM, PO, Transition manager, QA
10 |  | Application Setup | Setup application/Run application/run tests | Application is running/test scripts are running |  | High |  | Not Started |  |  | All prod server inventories, the purpose, deployment procedures, UAT procedures, release processes, DR operations (if any) | mvprash | KT Co-ordinator, Technical Architect, DevOps, KPMU (PM), SDC Team | Technical Architect, Technology Lead, BA DevOps, PM, PO, Transition manager, QA
11 | Phase 2 | Network | Share VPN, firewall, proxy, DNS, WAF and load balancer setup. | Network topology and access flow |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Technical Architect, DevOps, KPMU (PM), SDC Team | Technical Architect, Technology Lead, BA DevOps, PM, PO, Transition manager, QA
12 | Phase 2 | Security | Share authentication, authorization, secrets, certificates and privileged account process. | Security and access architecture |  | High |  | Not Started |  |  | SSO, role based access, ssl | mvprash | KT Co-ordinator, Technical Architect, DevOps, KPMU (PM), SDC Team | Technical Architect, Technology Lead, BA DevOps, PM, PO, Transition manager, QA, Security Specialist
13 | Phase 2 | Backup & DR | Share backup schedule, restore procedure | Backup and DR readiness report |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Technical Architect, KPMU (PM), SDC Team | Technical Architect, Technology Lead, BA DevOps, PM, PO, Transition manager, QA, DBA
14 | Phase 2 | Readiness Validation | Validate that application can run/access non-production environment with required dependencies. | Infrastructure readiness sign-off |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Technical Architect, DevOps, KPMU (PM), SDC Team | Technical Architect, Technology Lead, BA DevOps, PM, PO, Transition manager, QA, DBA, Full Stack Developers
15 | Phase 3 | Functional KT | Complete KT for registration, document management, citizen services, reports and integration workflows. | Functional KT notes and recordings |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Development Lead | BA, Full Stack Developers, QA, PO, Transition manager
16 | Phase 3 | Technical KT | Complete KT for Angular UI, .NET APIs, database design, integrations and security architecture. | Technical KT notes and design documents |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Development Lead, DBA, Tech lead, Security lead | UI/UX designer, BA, Full Stack developers, Technology Lead, Technical Architect, Security specialist, DBA, DB migration specialist
17 | Phase 3 | Operational KT | Complete KT for incident handling, monitoring, release, backup, file transfer and retry/reprocessing processes. | Operational SOPs |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, operation Lead, DBA, Tech lead, L2 support team | BA, Full Stack developers, Technology Lead, Technical Architect, DBA, DB migration specialist, L2 support team, PM , PO
18 | Phase 3 | KT Governance | Maintain KT session tracker with attendance, recording link, pending questions and sign-off status. | KT completion tracker |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator | Transition manager, PM, PO
19 | Phase 4 | DevOps | Review build process, dependencies, artifacts and build logs. | Build process document |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Devops | BA, Full Stack developers, Technology Lead, Technical Architect, DBA, DB , PM , PO, DevOps, Transition manager
20 | Phase 4 | DevOps | Review CI/CD pipelines, pipeline variables, approvals and deployment history. | Pipeline inventory and access evidence |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Devops | PM, PO, DevOps, , Transition manager
21 | Phase 4 | Release Management | Review release calendar, CAB/change approval process and release notes. | Release runbook |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Project Manager, DevOps | PM, PO, DevOps, Transition manager
22 | Phase 4 | Rollback | Review rollback &hotfix | Rollback checklist |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Devops | Devops, PM , PO, transition manager, Technical architect
23 | Phase 4 | Deployment Validation | Observe at least one non-production deployment end to end. | Deployment observation record |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Technical Architect, DevOps | DBA, Transition manager, architect, tech lead, pm , PO
24 | Phase 5 | Database | Review PostgreSQL/SQL Server inventory and module-to-database mapping. | Database inventory |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Development LEad, DBA | DBA, full stack developers, pm, po, transition expert, tech leads
25 | Phase 5 | Database | Obtain schema-level read access and validate access to required non-production DBs. | DB access confirmation |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Development LEad, DBA | DBA, full stack developers, pm, po, transition expert, tech leads
26 | Phase 5 | Database | Review ERD, data dictionary, stored procedures, functions and DB scripts. | DB design pack |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Development LEad, DBA | DBA, full stack developers, pm, po, transition expert, tech leads, Transition manager
27 | Phase 5 | Performance | Review largest tables, slow queries, indexes and recurring database bottlenecks. | Performance assessment notes |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Development LEad, DBA | Performance lead, DBA, QA, DBA, PM , PO, transition manager
28 | Phase 5 | Data Governance | Review backup, restore, archival, retention, purge | Data governance and DBA runbook |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, DBA, SDC team, technical archoitect | DBA, pm, po, transition expert, tech leads, Transition manager
29 | Phase 6 | Integrations | Prepare integration inventory covering Aadhaar, Sakala, Eaasthi, Payments, Treasury, Revenue, Local Bodies, Court, Income Tax, Reporting and others. | Integration inventory |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, BA, Technical Architect | Full stack developers, PM, BA, transition manager, PO, QA
30 | Phase 6 | Integrations | For each subsystem, capture API/file/DB/message integration type, endpoint, auth, data format and owner. | Interface and authentication matrix |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, BA, Development LEad, Technical Architect | Full stack developers, PM, BA, transition manager, PO, QA
31 | Phase 6 | File Transfers | Identify all file transfers: XML, scanned documents, payment reconciliation, reports, statutory extracts and fallback/manual transfers. | File transfer inventory |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, BA, Technical Architect, development lead | Full stack developers, PM, BA, transition manager, PO, QA
32 | Phase 6 | Failure Handling | Review retry, repush, reconciliation, monitoring and error-handling process for all integrations. | Integration runbook and error handling matrix |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, BA, Technical Architect, development lead | Full stack developers, PM, BA, transition manager, PO, QA
33 | Phase 6 | Test Readiness | Confirm sandbox/test endpoint availability and test credentials process. | External subsystem test readiness tracker |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Test Lead | tech architect, lead, pm , po, full stack developers, QA team
34 | Phase 7 | Operations | Review last 12 months incidents, Sev1/Sev2 issues, recurring issues, RCA and known workarounds. | Incident and known error report |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Operations Lead | L2 support, pm , po, transition manager
35 | Phase 7 | Monitoring | Review monitoring dashboards, alert thresholds, logs, escalation and support teams. | Monitoring handbook |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, BA, Technical Architect, development lead | L2 support, pm , po, transition manager
36 | Phase 7 | Support Model | Define L1/L2/L3 support responsibilities | Support model and escalation matrix |  | High |  | Not Started |  |  |  | mvprash | KT coordinator, pm, operations lead | L2 support, pm , po, transition manager
37 | Phase 7 | Runbooks | Finalize runbooks(If applicable) for application support, deployment, DB, integrations, file transfers, backup/DR and monitoring. | Support runbook pack |  | High |  | Not Started |  |  | currently as per me, there is no run books | mvprash
38 | Phase 8 | Shadow Support | Observe incident triage, troubleshooting, deployment, monitoring and integration recovery activities. | Shadow support observation log |  | High |  | Not Started |  |  |  | mvprash | KT coordinator, PM, Operations lead, dba, development lead | pm, po, full stack, dba, architect, lead, transition manager
39 | Phase 8 | Shadow Support | Document gaps discovered during shadow support and assign closure owners. | Gap tracker |  | High |  | Not Started |  |  |  | mvprash | KT Coordinator | pm, po, full stack, dba, architect, lead, transition manager
40 | Phase 9 | Reverse Shadow | Kyndryl team executes support activities while existing team observes. | Reverse shadow execution log |  | High |  | Not Started |  |  |  | mvprash | KT coordinator, PM, Operations lead, dba, development lead, technical architect | pm, po, full stack, dba, architect, lead, transition manager
41 | Phase 9 | Reverse Shadow | Perform operational readiness assessment and close critical gaps. | Readiness assessment |  | High |  | Not Started |  |  |  | mvprash | KT coordinator, PM, Operations lead, dba, development lead, technical architect | pm, po, full stack, dba, architect, lead, transition manager
41 | Phase 9 | Takeover | Agree production support takeover readiness criteria and sign-off. | Takeover sign-off |  | High |  | Not Started |  |  |  | mvprash | KT coordinator, PM, Operations lead, dba, development lead, technical architect | pm, po, full stack, dba, architect, lead, transition manager
42 | Phase 10 | Closure | Validate all transition exit criteria. | Exit criteria checklist |  | High |  | Not Started |  |  |  | mvprash | KT coordinator, PM, Operations lead, dba, development lead, technical architect | pm, po, full stack, dba, architect, lead, transition manager
43 | Phase 10 | Closure | Finalize handover pack and archive all documents. | Final handover pack |  | High |  | Not Started |  |  |  | mvprash | KT coordinator, PM, Operations lead, dba, development lead, technical architect | pm, po, full stack, dba, architect, lead, transition manager
44 | Phase 10 | Closure | Obtain formal sign-off from incumbent team, customer and Kyndryl stakeholders. | Transition closure sign-off |  | High |  | Not Started |  |  |  | mvprash | KT coordinator, PM, Operations lead, dba, development lead, technical architect | pm, po, full stack, dba, architect, lead, transition manager

## Week 1 Planning
Week 1 & 2
Step | Status | Focal - CSG/Service Desk | Kaveri IT Cell Team | Owner- IT Cell | Artifacts Included | Start Date | End Date | Outlook Date | Comments
Identify Communication Methods with CSG Team |  | TBD | Transition Manager | Transition /PM | List of contact person details with designation | 28th July | 28th July |  | TBD if F2F only or Chat/E-mails
Walk through of the Kaveri 2.0 Portal |  | Vishwanath (AM - CMS) | BA, Developers, PM. Net developers | BA | User Manuals, training Videos | 5th August | 7th August
Walk Through of the Exisiting BAU activities of the CSG team |  | Devops | DevOps | Dev Ops | SOP's/ Runbooks | 10th August | 12th August
Identify existing infrastructure and cross verify with whats procured by IT Cell |  | Technical Architect | Technical Architect | Technical Architect | Kaveri IT Cell, IT Infrastructure document | 5th August | 5th August
Understanding Existing Environment Available(UAT, Prepord, Prod etc) & getting Access |  | DevOps, Tech Architect | Dev Ops, Developers, Tech Architect | Technical Architect | Existing DB architecture document, System Architecture document | 10th August | 12th August
Identifying & Provide Read access to the Source Code Repositories |  | Software development Team & Dev Ops | Software development Team(.Net developers) & Dev Ops | Dev Ops |  | 10th August | 14th August
Read Only access to the Data base |  | DB Admin | DBA |  | Credentials document for access | 10th August | 14th August |  | Understrand how the existing Tables Indexes, Objects etc are created
Walkthrough of the Technolgies used & Existing code |  | Technical Architect, Developer's | Technical Architect, Developer's | Technical Architect | Tech Stack Document | 17th August | 21st August

## Kaveri 2.0 Transition
Week 1
Task # | Task Name | Owner/Focal - CSG/Service Desk | Kaveri IT Cell Team | Owner- IT Cell | Comments | Artifacts Included | Status | Start Date | End Date
1 | Identify Communication Methods with CSG Team | TBD | Transition Manager | Transition /PM | TBD if F2F or Online
1.1 | Whats the mode of communication with the CSG team -Chat/Calls (MS, Google) |  | Transition Manager
1.2 | Repository for Document sharing - If access to be provided to CSG Repsoitory of existing documents /Videos or IT Cell to maintain a new one
1.3 | Can KT & Trainings from CSG be recorded and majntained by IT Cell
2 | Walk Through of the Exisitng BAU activities of the CSG team | Vishwanath (AM - CMS) | BA, Developers, PM. Net developers | BA |  | User Manuals, training Videos
2.1 | Define Roles of each CSG member
| Understanding Existing Environment Available(UAT, Prepord, Prod etc) | DevOps, Tech Architect | Dev Ops, Developers, Tech Architect | Tech Architect |  | Existing DB architecture document, System Architecture document
| Identifying the Source Code for Repositories | Software development Team & Dev Ops | Software development Team(.Net developers) & Dev Ops | Dev Ops
| Provide Read Access to Source Codes | Dev Ops | Software development Team(.Net developers) & Dev Ops | Dev Ops

## Resource List & Focals
Focals
CSG/ Service Desk | IT Cell