## Detailed KT Plan
Sl No | Phase | Workstream | Activity / Task | Expected Output / Evidence | Dependency | Priority | Owner / SME | Status | Target Date | Remarks | Comments | Comments By | CSG Role/KPMU | Kaveri IT Cell
1 | Phase 1 | Application Discovery | Identify all Kaveri application modules and business functions. | Application/module inventory | Column1 | High | Column2 | Not Started | Column3 | Completed |  |  | Completed
2 | Phase 1 | Application Discovery | Conduct application walk-through for citizen, sub-registrar, admin, reporting and support flows. | Walkthrough notes and demo recordings |  | High |  | Not Started |  | Support of AI Tool like copilot will be helpful | 1. Document Registration 2. Marriage Registration 3. Firm Registration 4. Society Registration 5. Market Value Estimation 6. Stamp Duty Calculation 7. Registration Fee Calculation 8. Section 68 module 9. Liability Entry module 10. Scanning module 11. DSC Signing module 12. Encumbrance Certificate 13. Certified Copy 14. Accounting Module 15. Appointment Scheduling 16. User Management 17. Court Order Management 18. Workflow Management 19. Notification Services 20. Reporting & MIS 21. Paperless Registration, | added module list, mvprash | KT Co-ordinator, BA | Full Stack Developers, BA, PM, PO, Transition manager, Technical architect
3 | Phase 1 | Source Code | Identify source code repositories for UI, APIs, services, scripts, reports and database scripts. | Repository inventory with URLs |  | High |  | Not Started |  |  | Know -> Purpose of the code, Build process, dependencies, Branch structure and deployment processes | mvprash | KT Co-ordinator, DevOps | DevOps, PM, PO, Transition manager
4 | Phase 1 | Source Code | Obtain read access to source repositories and validate access with sample checkout. | Access confirmation and sample checkout evidence | Access approval | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Development Lead, DevOps | Full Stack Developers, DevOps, PM, PO, Transition manager
5 | Phase 1 | Environment | Identify Dev, SIT, Pre-Prod, Prod, environments. | Environment inventory |  | High |  | Not Started |  |  | add staging | mvprash | KT Co-ordinator, Development Lead Technical Architect, DevOps | Full Stack Developers, DevOps, PM, PO, Transition manager
6 | Phase 1 | Environment | Share environment URLs, login process, VPN/VDI/bastion requirements and access approvers. | Environment access matrix |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Technical Architect, DevOps | Technical Architect, Technology Lead, BA DevOps, PM, PO, Transition manager
7 | Phase 1 | Access Readiness | Provide access for application, source code, DevOps, DB, infra, monitoring, logs and file/object store. | Access tracker | Approver list | High |  | Not Started |  |  | as read-only, provide git hub accounts/credentials | mvprash | KT Co-ordinator, Technical Architect, DevOps, KPMU (PM), SDC Team | Technical Architect, Technology Lead, BA DevOps, PM, PO, Transition manager, DBA
8 | Phase 2 | Infrastructure Readiness | Review current hosting model: data center, VM, container, DockerDesktop or mixed. Share the application and infrastructure topology | Infrastructure topology |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Technical Architect, DevOps, KPMU (PM), SDC Team | Technical Architect, Technology Lead, BA DevOps, PM, PO, Transition manager, QA
9 | Phase 2 | Infrastructure Readiness | Share server inventory, resource allocation, OS/runtime versions and ownership. | Server inventory |  | High |  | Not Started |  |  | All prod server inventories, the purpose, deployment procedures, UAT procedures, release processes, DR operations (if any) | mvprash | KT Co-ordinator, Technical Architect, DevOps, KPMU (PM), SDC Team | Technical Architect, Technology Lead, BA DevOps, PM, PO, Transition manager, QA
10 |  | Application Setup | Setup application/Run application/run tests | Application is running/test scripts are running |  | High |  | Not Started |  |  | All prod server inventories, the purpose, deployment procedures, UAT procedures, release processes, DR operations (if any) | mvprash | KT Co-ordinator, Technical Architect, DevOps, KPMU (PM), SDC Team | Technical Architect, Technology Lead, BA DevOps, PM, PO, Transition manager, QA
11 | Phase 2 | Network | Share VPN, firewall, proxy, DNS, WAF and load balancer setup. | Network topology and access flow |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Technical Architect, DevOps, KPMU (PM), SDC Team | Technical Architect, Technology Lead, BA DevOps, PM, PO, Transition manager, QA
12 | Phase 2 | Security | Share authentication, authorization, secrets, certificates and privileged account process. | Security and access architecture |  | High |  | Not Started |  |  | SSO, role based access, ssl | mvprash | KT Co-ordinator, Technical Architect, DevOps, KPMU (PM), SDC Team | Technical Architect, Technology Lead, BA DevOps, PM, PO, Transition manager, QA, Security Specialist
13 | Phase 2 | Backup & DR | Share backup schedule, restore procedure, DR environment, RPO/RTO and last restore validation evidence. | Backup and DR readiness report |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Technical Architect, KPMU (PM), SDC Team | Technical Architect, Technology Lead, BA DevOps, PM, PO, Transition manager, QA, DBA
14 | Phase 2 | Readiness Validation | Validate that application can run/access non-production environment with required dependencies. | Infrastructure readiness sign-off |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Technical Architect, DevOps, KPMU (PM), SDC Team | Technical Architect, Technology Lead, BA DevOps, PM, PO, Transition manager, QA, DBA, Full Stack Developers
15 | Phase 3 | Functional KT | Complete KT for registration, document management, citizen services, reports and integration workflows. | Functional KT notes and recordings |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Development Lead | BA, Full Stack Developers, QA, PO, Transition manager
16 | Phase 3 | Technical KT | Complete KT for Angular UI, .NET APIs, database design, integrations and security architecture. | Technical KT notes and design documents |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Development Lead, DBA, Tech lead, Security lead | UI/UX designer, BA, Full Stack developers, Technology Lead, Technical Architect, Security specialist, DBA, DB migration specialist
17 | Phase 3 | Operational KT | Complete KT for incident handling, monitoring, release, backup, file transfer and retry/reprocessing processes. | Operational SOPs |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, operation Lead, DBA, Tech lead, L2 support team | BA, Full Stack developers, Technology Lead, Technical Architect, DBA, DB migration specialist, L2 support team, PM , PO
18 | Phase 3 | KT Governance | Maintain KT session tracker with attendance, recording link, pending questions and sign-off status. | KT completion tracker |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator | Transition manager, PM, PO
19 | Phase 4 | DevOps | Review build process, dependencies, artifacts and build logs. | Build process document |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Devops | BA, Full Stack developers, Technology Lead, Technical Architect, DBA, DB , PM , PO, DevOps, Transition manager
20 | Phase 4 | DevOps | Review CI/CD pipelines, pipeline variables, approvals and deployment history. | Pipeline inventory and access evidence |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Devops | PM, PO, DevOps, , Transition manager
21 | Phase 4 | Release Management | Review release calendar, CAB/change approval process and release notes. | Release runbook |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Project Manager, DevOps | PM, PO, DevOps, Transition manager
22 | Phase 4 | Rollback | Review rollback, hotfix and emergency deployment process. | Rollback checklist |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Devops | Devops, PM , PO, transition manager, Technical architect
23 | Phase 4 | Deployment Validation | Observe at least one non-production deployment end to end. | Deployment observation record |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Technical Architect, DevOps | DBA, Transition manager, architect, tech lead, pm , PO
24 | Phase 5 | Database | Review PostgreSQL/SQL Server inventory and module-to-database mapping. | Database inventory |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Development LEad, DBA | DBA, full stack developers, pm, po, transition expert, tech leads
25 | Phase 5 | Database | Obtain schema-level read access and validate access to required non-production DBs. | DB access confirmation |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Development LEad, DBA | DBA, full stack developers, pm, po, transition expert, tech leads
26 | Phase 5 | Database | Review ERD, data dictionary, stored procedures, functions and DB scripts. | DB design pack |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Development LEad, DBA | DBA, full stack developers, pm, po, transition expert, tech leads, Transition manager
27 | Phase 5 | Performance | Review largest tables, slow queries, indexes and recurring database bottlenecks. | Performance assessment notes |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Development LEad, DBA | Performance lead, DBA, QA, DBA, PM , PO, transition manager
28 | Phase 5 | Data Governance | Review backup, restore, archival, retention, purge and PII handling process. | Data governance and DBA runbook |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, DBA, SDC team, technical archoitect | DBA, pm, po, transition expert, tech leads, Transition manager
29 | Phase 6 | Integrations | Prepare integration inventory covering Aadhaar, Sakala, Eaasthi, Payments, Treasury, Revenue, Local Bodies, Court, Income Tax, Reporting and others. | Integration inventory |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, BA, Technical Architect | Full stack developers, PM, BA, transition manager, PO, QA
30 | Phase 6 | Integrations | For each subsystem, capture API/file/DB/message integration type, endpoint, auth, data format and owner. | Interface and authentication matrix |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, BA, Development LEad, Technical Architect | Full stack developers, PM, BA, transition manager, PO, QA
31 | Phase 6 | File Transfers | Identify all file transfers: XML, scanned documents, payment reconciliation, reports, statutory extracts and fallback/manual transfers. | File transfer inventory |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, BA, Technical Architect, development lead | Full stack developers, PM, BA, transition manager, PO, QA
32 | Phase 6 | Failure Handling | Review retry, repush, reconciliation, monitoring and error-handling process for all integrations. | Integration runbook and error handling matrix |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, BA, Technical Architect, development lead | Full stack developers, PM, BA, transition manager, PO, QA
33 | Phase 6 | Test Readiness | Confirm sandbox/test endpoint availability and test credentials process. | External subsystem test readiness tracker |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Test Lead | tech architect, lead, pm , po, full stack developers, QA team
34 | Phase 7 | Operations | Review last 12 months incidents, Sev1/Sev2 issues, recurring issues, RCA and known workarounds. | Incident and known error report |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, Operations Lead | L2 support, pm , po, transition manager
35 | Phase 7 | Monitoring | Review monitoring dashboards, alert thresholds, logs, escalation and support teams. | Monitoring handbook |  | High |  | Not Started |  |  |  | mvprash | KT Co-ordinator, BA, Technical Architect, development lead | L2 support, pm , po, transition manager
36 | Phase 7 | Support Model | Define L1/L2/L3 support responsibilities, SLAs, escalation matrix and operating hours. | Support model and escalation matrix |  | High |  | Not Started |  |  |  | mvprash | KT coordinator, pm, operations lead | L2 support, pm , po, transition manager
37 | Phase 7 | Runbooks | Finalize runbooks for application support, deployment, DB, integrations, file transfers, backup/DR and monitoring. | Support runbook pack |  | High |  | Not Started |  |  | currently as per me, there is no run books | mvprash
38 | Phase 8 | Shadow Support | Observe incident triage, troubleshooting, deployment, monitoring and integration recovery activities. | Shadow support observation log |  | High |  | Not Started |  |  |  | mvprash | KT coordinator, PM, Operations lead, dba, development lead | pm, po, full stack, dba, architect, lead, transition manager
39 | Phase 8 | Shadow Support | Document gaps discovered during shadow support and assign closure owners. | Gap tracker |  | High |  | Not Started |  |  |  | mvprash | KT Coordinator | pm, po, full stack, dba, architect, lead, transition manager
40 | Phase 9 | Reverse Shadow | Kyndryl team executes support activities while existing team observes. | Reverse shadow execution log |  | High |  | Not Started |  |  |  | mvprash | KT coordinator, PM, Operations lead, dba, development lead, technical architect | pm, po, full stack, dba, architect, lead, transition manager
41 | Phase 9 | Reverse Shadow | Perform operational readiness assessment and close critical gaps. | Readiness assessment |  | High |  | Not Started |  |  |  | mvprash | KT coordinator, PM, Operations lead, dba, development lead, technical architect | pm, po, full stack, dba, architect, lead, transition manager
41 | Phase 9 | Takeover | Agree production support takeover readiness criteria and sign-off. | Takeover sign-off |  | High |  | Not Started |  |  |  | mvprash | KT coordinator, PM, Operations lead, dba, development lead, technical architect | pm, po, full stack, dba, architect, lead, transition manager
42 | Phase 10 | Closure | Validate all transition exit criteria. | Exit criteria checklist |  | High |  | Not Started |  |  |  | mvprash | KT coordinator, PM, Operations lead, dba, development lead, technical architect | pm, po, full stack, dba, architect, lead, transition manager
43 | Phase 10 | Closure | Finalize handover pack and archive all documents. | Final handover pack |  | High |  | Not Started |  |  |  | mvprash | KT coordinator, PM, Operations lead, dba, development lead, technical architect | pm, po, full stack, dba, architect, lead, transition manager
44 | Phase 10 | Closure | Obtain formal sign-off from incumbent team, customer and Kyndryl stakeholders. | Transition closure sign-off |  | High |  | Not Started |  |  |  | mvprash | KT coordinator, PM, Operations lead, dba, development lead, technical architect | pm, po, full stack, dba, architect, lead, transition manager

## QA and Testing
Sl No | Workstream | Activity / Task | Expected Output / Evidence | Dependency | Priority | Owner / SME | Status | Target Date | Remarks
1 | Application Discovery | End to End Functional flow for all the modules are required | Conduct Knowledge Transfer sessions for each modules |  | High
2 | Application Discovery | Share the Consolidated FRD's and Azure Devops Requirement links | Share the Consolidated FRD's and Azure Devops Requirement links |  | High
3 | Environment | Identify Stage, SIT, Pre-Prod, Prod, environments. | Environment inventory |  | High
4 | Environment | Share environment URLs, login process, VPN/VDI and access approvers. | Environment access matrix |  | High
5 | TestData | Conduct Walkthrough on how to create or how get the test data | Test data Walkthrough |  | High
6 | Automation Testing | Conduct Walkthrough on What can be automated and what cant be automated | Conduct KT session on Automation testing |  | High
7 | Database | Conduct Walkthrogh on DB[Access, Validations] | Conduct KT session on DB |  | High
8 | UAT | Conduct Walkthrough on how the UAT will be Performed | Conduct KT session on UAT |  | High
9 | Non Functional Testing | What is the scope for Non functional Testing | Conduct KT session on Non Functional Testing |  | High
10 | Back End Testing | Provide a BackEnd Testing walkthrough[API's] | Conduct KT session on Back End testing |  | High

## Infrastructure Readiness
Infrastructure Readiness Checklist
Readiness checklist to confirm hosting, network, security, backup/DR, observability, access and operational stability before full handover.
1 | Hosting | Confirm hosting model | Data center/cloud/VM/container/Kubernetes/OpenShift; runtime versions; resource allocation. | Infrastructure topology and server inventory | Column1 | Not Started | Application cannot be operated independently | Column2 | Column3
2 | Application Runtime | Confirm application can run in non-prod | Validate URLs, login, services, configs, dependencies and test data. | Access evidence and smoke test result |  | Not Started | Discovery blocked if app cannot be exercised
3 | Server Inventory | Document servers/nodes | Hostname, IP, OS, CPU, RAM, disk, environment, owner and criticality. | Server inventory |  | Not Started | Support and capacity planning gaps
4 | Network | Validate connectivity path | VPN/VDI/bastion, firewall, proxy, DNS, WAF, load balancer and IP allowlists. | Network diagram and access steps |  | Not Started | Access delays and integration failures
5 | Security | Review authentication and authorization | User roles, service accounts, privileged users, access approvals and audit logs. | Security design and role matrix |  | Not Started | Unauthorized access or support gaps
6 | Secrets & Certificates | Capture certificate and secret inventory | Certificates, API keys, tokens, vault/keystore, expiry dates and rotation ownership. | Certificate/secret register |  | Not Started | Integration or login failure after expiry
7 | Database | Validate DB connectivity and access | PostgreSQL/SQL Server access, schema, query stats, DB tools and approvers. | DB access validation |  | Not Started | Unable to troubleshoot data and performance issues
8 | Storage | Validate file/object store access | Document store, XML/report folders, object storage buckets, retention and access controls. | Storage/folder inventory |  | Not Started | File processing and document retrieval gaps
9 | Monitoring | Review monitoring dashboards | Availability, performance, log dashboards, alert rules and escalation contacts. | Monitoring dashboard list |  | Not Started | Incidents may go undetected
10 | Logging | Confirm centralized logs | UI, API, DB, integration, file transfer and infrastructure logs with retention. | Log architecture and sample trace |  | Not Started | Troubleshooting delays
11 | Backup | Review backup process | Schedule, scope, retention, backup owner, backup logs and restore process. | Backup policy and logs |  | Not Started | Data recovery risk
12 | Disaster Recovery | Review DR setup | DR environment, failover process, RPO/RTO, last DR drill and restore evidence. | DR runbook and drill evidence |  | Not Started | Business continuity risk
13 | Capacity | Assess current utilization | CPU, memory, storage, DB growth, peak load and headroom. | Capacity/utilization report |  | Not Started | Performance risk
14 | Compliance | Review compliance controls | PII, encryption, audit trails, data retention and regulatory obligations. | Compliance checklist / audit notes |  | Not Started | Audit or regulatory exposure

## RAID and Open Items
RAID Log and Open Items
Use this sheet to track transition risks, assumptions, issues, dependencies and open actions discovered during the Kaveri handover.
R-001 | Risk | Production or lower-environment access is delayed or incomplete. | Discovery and support readiness may be delayed. | High | Column1 | Column2 | Not Started | Track access requests daily and escalate pending approvals. | Column3 | Column4
R-002 | Risk | Source code, pipeline or deployment documentation is incomplete. | Build/release handover may remain dependent on incumbent team. | High |  |  | Not Started | Conduct repository and pipeline walkthrough; capture missing artifacts.
R-003 | Risk | Infrastructure details such as server inventory, network routes, WAF/load balancer and DR setup are not fully documented. | Operational readiness and troubleshooting may be impacted. | High |  |  | Not Started | Create infrastructure readiness checklist and validate with infra SMEs.
R-004 | Risk | External subsystem authentication and file transfer details are not known. | Integration troubleshooting and onboarding may be impacted. | High |  |  | Not Started | Complete integration inventory, auth matrix and file transfer checklist.
A-001 | Assumption | Existing maintenance team will provide SMEs for functional, technical, DevOps, DB, infrastructure and integration walkthroughs. | KT completion depends on SME availability. | Medium |  |  | Not Started | Publish KT calendar and track attendance/sign-offs.
D-001 | Dependency | Access approvals are required for repositories, DevOps, DB, infra, monitoring, logs and file/object store. | Access readiness depends on customer/incumbent approvals. | High |  |  | Not Started | Use access tracker and obtain named approvers.
I-001 | Issue | Exact file transfer protocols and authentication mechanisms are currently to be confirmed. | Cannot finalize integration and security handover until confirmed. | High |  |  | Not Started | Review integration documentation and request live walkthrough of file processing/reconciliation.