## W1 Day Checklist
Kaveri 2.0 → IT Cell Transition ¦ TE Week 1 Checklist (Mobilise + Discover)
TE owns: schedule → chase CSG → collect evidence → update tracker → gate. Week 1 exit: inventories started + access requests submitted.
Day | Time | TE Task | Support | Evidence / Output | Done (Y/N) | Evidence Link | Blocker / Remark
Day 1 Mon | AM | Kickoff with PM/PO: scope, roles, reporting cadence | PM, PO | Transition charter (1–2 pg)
Day 1 Mon | AM | Freeze phase exit criteria (W1 + overall takeover) | PM, PO | Exit criteria v1 agreed
Day 1 Mon | PM | Stand up master tracker (KT rows 1–7 + control items) | PM | Live tracker created
Day 1 Mon | PM | Create RAID + dependency map (CSG, SDC, KPMU, approvers) | PM | RAID log seeded
Day 1 Mon | PM | Draft W1–W2 calendar + daily 15-min stand-up | PM, PO | Calendar invite pack
Day 1 Mon | EOD | Confirm CSG KT contact + response SLA | CSG, PM | Named CSG point + channel
Day 2 Tue | AM | Chase module/business inventory (#1) | BA, CSG | Module inventory draft ≥80%
Day 2 Tue | AM | Tag modules: in-scope / owner / walkthrough Y/N | BA | Module coverage matrix
Day 2 Tue | PM | Book walkthroughs (#2): citizen, SR, admin, report, support | BA, Dev, Arch, PM, PO | Walkthrough calendar booked
Day 2 Tue | PM | Publish walkthrough template + Q&A log | BA | Checklist + Q&A template
Day 2 Tue | EOD | Update tracker; log CSG blockers | PM | Status + RAID update
Day 3 Wed | AM | Chase repo inventory (#3): UI/API/services/scripts/DB | DevOps, CSG | Repo list + URLs (or pending)
Day 3 Wed | AM | Capture purpose / branch / build / deploy note per repo | DevOps, Dev | Repo inventory columns filled
Day 3 Wed | PM | Submit repo read-access requests (#4) — read-only GitHub | DevOps, Dev, SDC | Access request pack submitted
Day 3 Wed | PM | Define evidence rule (checkout screenshot / clone log) | DevOps, Dev | Evidence folder + naming
Day 3 Wed | EOD | Publish chase list: who owes URL / approval | CSG, DevOps | Open chase list w/ due dates
Day 4 Thu | AM | Build env inventory (#5): Dev/SIT/Staging/PreProd/Prod | Arch, DevOps | Env matrix v1
Day 4 Thu | AM | Collect URLs, login, VPN/VDI/bastion, approvers (#6) | Arch, DevOps, BA | Env access matrix draft
Day 4 Thu | PM | Build master access tracker (#7): app/code/DB/logs/monitor/store | Arch, DevOps, DBA, SDC | Access tracker live
Day 4 Thu | PM | Route pending approvals to named approvers | Arch, DevOps, DBA, SDC, KPMU | Approval tickets/mails sent
Day 4 Thu | EOD | Prioritise critical path: VPN + app + git + DB read | PM | Priority access shortlist
Day 5 Fri | AM | File proofs for any granted access (login/checkout) | DevOps, Dev, DBA | Evidence pack (partial OK)
Day 5 Fri | AM | Run Week 1 exit review vs exit criteria | PM, PO | Gate: Pass / Conditional / Fail
Day 5 Fri | PM | Publish Week 1 status report | PM, PO | 1-page weekly status
Day 5 Fri | PM | Lock Week 2 agenda (infra/topology/network/security/BKP/DR) | Arch, DevOps, SDC | W2 calendar holds + CSG slots
Day 5 Fri | PM | Escalate access blockers >3 days | PM, PO | Escalation list
Day 5 Fri | EOD | Draft handover pack ToC + early shadow window holds | PM, Ops | Handover ToC + shadow holds
WEEK 1 EXIT CHECKLIST (TE owns)
# | Item | Pass rule | Status | Evidence | Owner Support | Risk if fail | Remark
— | Exit criteria + RAID + tracker | Created & agreed |  |  | PM, PO | No control baseline
1 | Module inventory | Started; major modules listed |  |  | BA, CSG | KT calendar blocked
2 | Walkthroughs | Calendar booked (sessions may start W2) |  |  | BA, Dev, Arch | Discovery delay
3 | Repo inventory | List started; URLs chased |  |  | DevOps, CSG | Code KT blocked
4 | Repo read access | Requests submitted; grants have checkout proof |  |  | DevOps, Dev | No code visibility
5 | Env inventory | Dev/SIT/Staging/PreProd/Prod named |  |  | Arch, DevOps | Env readiness slip
6 | Env access matrix | URLs + VPN/VDI + approvers captured/chased |  |  | Arch, DevOps, BA | Teams locked out
7 | Access pack tracker | All critical rows = request submitted |  |  | Arch, DevOps, DBA, SDC | W2 cannot start
Note: Do NOT wait for 100% access grants in W1. Pass = requests in + inventories started. Full access proven is stretch if CSG/SDC are fast.

## Tracker Template
TE Master Tracker — Column Template (use for W1 Discovery + Access; extend for later phases)
Fill one row per KT Plan activity. TE updates Status / Evidence / Chase daily. Support does technical work.
Sl No | Phase | Workstream | Activity / Task | Expected Evidence | TE Action | Support Roles | Priority | Target Date | Status | Access Req ID / Ticket | Evidence Link | Blocker / RAID Ref | Remarks
Status values: Not Started ¦ Chased ¦ In Progress ¦ Request Submitted ¦ Evidence Pending ¦ Done ¦ Blocked
CTL-01 | P0 Mobilise | Plan & Control | Freeze exit criteria, calendar, RAID | Approved exit criteria + RAID + calendar | Own | PM, PO | High |  | Not Started
1 | Phase 1 | Application Discovery | Identify all Kaveri modules and business functions | Application/module inventory | Own tracker | BA, CSG | High |  | Not Started
2 | Phase 1 | Application Discovery | Conduct walkthroughs: citizen, SR, admin, reporting, support | Walkthrough notes + recordings | Schedule + tracker | BA, Dev, Arch, PM, PO | High |  | Not Started
3 | Phase 1 | Source Code | Identify repos for UI, APIs, services, scripts, reports, DB scripts | Repository inventory with URLs | Chase list | DevOps, CSG | High |  | Not Started
4 | Phase 1 | Source Code | Obtain read access + validate with sample checkout | Access confirmation + checkout evidence | Track evidence | DevOps, Dev | High |  | Not Started
5 | Phase 1 | Environment | Identify Dev, SIT, Staging, Pre-Prod, Prod | Environment inventory | Own matrix | Arch, DevOps | High |  | Not Started
6 | Phase 1 | Environment | Share env URLs, login, VPN/VDI/bastion, approvers | Environment access matrix | Own access matrix | Arch, DevOps, BA | High |  | Not Started
7 | Phase 1 | Access Readiness | Access for app, code, DevOps, DB, infra, monitoring, logs, store | Access tracker (request→grant→prove) | Own access tracker | Arch, DevOps, DBA, SDC, KPMU | High |  | Not Started
ACCESS SUB-TRACKER (expand row #7) — one line per system
System | Type | Env | Access Level | Approver | Request Date | Ticket / Mail Ref | Status | Granted Date | Proven By (login/checkout) | Evidence Link | IT Cell User(s) | Chase Owner (TE) | Remarks
Kaveri App (Citizen) | Application | Non-Prod | Read / Demo |  |  |  | Not Started |  |  |  |  | TE
Kaveri App (SR / Admin) | Application | Non-Prod | Read / Demo |  |  |  | Not Started |  |  |  |  | TE
Source Repos (GitHub) | Code | All | Read-only |  |  |  | Not Started |  |  |  |  | TE
CI/CD / DevOps tools | DevOps | Non-Prod | Read |  |  |  | Not Started |  |  |  |  | TE
Database | DB | Non-Prod | Schema read |  |  |  | Not Started |  |  |  |  | TE
VPN / VDI / Bastion | Network | All | Connect |  |  |  | Not Started |  |  |  |  | TE
Monitoring / Alerts | Ops | Non-Prod | Read |  |  |  | Not Started |  |  |  |  | TE
Logs | Ops | Non-Prod | Read |  |  |  | Not Started |  |  |  |  | TE
File / Object Store | Storage | Non-Prod | Read |  |  |  | Not Started |  |  |  |  | TE
COLUMN GUIDE
Sl No | Map to Detailed KT Plan row number (or CTL-xx for control tasks)
TE Action | Own ¦ Schedule + tracker ¦ Chase list ¦ Track evidence ¦ Own matrix ¦ Gate
Status | Use controlled list above; TE updates daily in stand-up
Access Req ID | Ticket/mail ID for every access row — no verbal-only requests
Evidence Link | SharePoint/Drive path or screenshot; empty = not done
Blocker / RAID Ref | Link to RAID ID (R-01, A-02…); escalate if age >3 days

## Day1 Kickoff Mail
Day 1 Kickoff Mail — Copy/paste ready
To: | [PM], [PO], [CSG KT Lead], [IT Cell Leads: Arch / DevOps / BA / Dev], [KPMU]
Cc: | [SDC contact], [TE manager]
Subject: | Kaveri Transition Kickoff — Week 1 Mobilise & Discover (CSG → IT Cell) ¦ Action required
Body:
Team, The Transition Expert (TE) has joined to drive the Kaveri 2.0 (CSG) → Kaveri IT Cell handover. Week 1 focus (Mobilise + Discover): 1. Freeze exit criteria, calendar, and RAID 2. Module / business inventory 3. Schedule application walkthroughs (citizen / SR / admin / reporting / support) 4. Source-repo inventory + read-access requests 5. Environment inventory (Dev / SIT / Staging / PreProd / Prod) + access matrix 6. Master access tracker for app, code, DB, logs, monitoring, and file store TE role: plan, schedule, chase, collect evidence, and gate — not deep tech delivery. Support roles (BA / Arch / Dev / DevOps / DBA / SDC / CSG): produce inventories, grant access, and run demos. Week 1 exit (Fri): inventories started + all critical access requests submitted. Actions requested by EOD Day 1: • PM/PO — confirm exit criteria owners and approve W1 calendar • CSG — name KT single point of contact and confirm response SLA • DevOps/CSG — share repo URL list (or confirm date) • Arch/DevOps — share env list + VPN/VDI/approver contacts • All IT Cell leads — send names needing access (app / git / DB / VPN) Working rhythm: • Daily 15-min stand-up (TE hosts): done / today / blockers / decisions • Tracker + RAID will be shared after kickoff Please reply with your named contacts and any known access constraints. Regards, [TE Name] Transition Expert — Kaveri IT Cell
Daily stand-up card (TE asks)
1. What evidence was filed yesterday? 2. What will be chased / closed today? 3. Blockers (access / CSG / SDC)? 4. Any decision needed from PM/PO today?

## RAID Seed
Week 1 RAID Seed (TE owns; update daily)
ID | Type (R/A/I/D) | Description | Impact | Owner | Due | Status | Escalation Path | Remarks
R-01 | Risk | CSG slow on module/repo inventory | W1 exit slip; KT calendar slips | TE / CSG |  | Open | PM → KPMU
R-02 | Risk | Access approvals delayed (VPN/git/DB) | No discovery evidence; W2 blocked | TE / Approvers |  | Open | PM → SDC/KPMU
R-03 | Risk | Walkthrough attendees unavailable | Functional discovery incomplete | TE / BA |  | Open | PO
A-01 | Assumption | Non-prod access sufficient for W1–W2 | If prod-only needed, escalate early | TE / Arch |  | Open | PM
A-02 | Assumption | Read-only GitHub accounts will be issued | If org policy blocks, need alt path | TE / DevOps |  | Open | SDC
I-01 | Issue | (log as raised) |  | TE |  | Open | PM
D-01 | Dependency | Named CSG KT contact + SLA | All chases blocked without it | CSG / PM | Day 1 | Open | KPMU
D-02 | Dependency | Approver list for app/code/DB/VPN | Access pack cannot close | Arch / SDC | Day 4 | Open | KPMU