## Slide 1
KAVERI 3.0
Programme Delivery Plan
Phase-wise SDLC · 11-month Go Live · Data Migration from Kaveri 1.0 / 2.0
Department of Stamps & Registration | Government of Karnataka
PLAN-K3-PROG-001 · Version 0.4 (Draft) · August 2026

## Slide 2
Agenda
Steering review pack
Kaveri 3.0 Programme Plan v0.4 | PLAN-K3-PROG-001 | Confidential — Steering
2/14
1. Programme constraints & objectives
2. Four delivery phases — scope
3. Master timeline & Go Live dates
4. Phase 1 deep-dive (21 Oct 2026)
5. Phases 2–4 summary
6. SDLC stages per phase
7. IT Cell resources (39 posts)
8. Data migration from Kaveri 1.0 / 2.0
9. Governance, gates & key risks
10. Decisions requested

## Slide 3
Hard programme constraints
Non-negotiables for planning
Kaveri 3.0 Programme Plan v0.4 | PLAN-K3-PROG-001 | Confidential — Steering
3/14
T0 — Start
17 August 2026
BR schedule kick-off
Requirements window opens
Phase 1 Go Live
3rd week of October 2026
Target: 21 October 2026
~9-week all-hands sprint
All modules live
Within 11 months
End: 16 July 2027
Phase 4 GL: 14 July 2027
Data Migration
Kaveri 1.0 + 2.0 in scope
Cutover with each phase
Exit report mandatory
Implications
• Phase 1 is the pathfinder — platform (User Mgmt, eKYC, eSign, Khajane, Scanning) ships first
• Phases 2–4 run in parallel after 21 Oct with squad rebalance (8 Full Stack)
• Phase 3 (Document Registration + EC + migration volume) is the critical path
• No phase Go Live without Migration Exit Report + legacy freeze/delta cutover

## Slide 4
Business objectives
What success looks like
Kaveri 3.0 Programme Plan v0.4 | PLAN-K3-PROG-001 | Confidential — Steering
4/14
# | Objective | Measure
O1 | All modules live in 11 months; P1 by 3rd week Oct 2026 | P1 ≤ 21-10-2026; P4 ≤ 16-07-2027
O2 | Statutory compliance (Registration / Stamp Acts & Rules) | Legal / Domain template & fee lock
O3 | Shared platform once (identity, eKYC, eSign, Khajane, scan) | Reuse across phases — no duplicate stacks
O4 | Deliver within IT Cell capacity | 39 posts — wave allocation
O5 | e-Gov NFR bar | GIGW, WCAG, STQC/security, HA/DR
O6 | Migrate Kaveri 1.0/2.0 data safely | Reconcile + exit report per phase

## Slide 5
Delivery phases — scope
Four releases; one programme
Kaveri 3.0 Programme Plan v0.4 | PLAN-K3-PROG-001 | Confidential — Steering
5/14
Phase 1
21 Oct 2026
• Marriage (Online + Offline)
• Certified Copies (CC)
• User Management
• eKYC · eSign · Khajane
• Scanning · Marriage MIS/Dash
• DM-P1 masters/users/marriage
Phase 2
16 Mar 2027
• Stamp Duty Calculator
• Guideline Value Calculator
• Market Valuator (CVC)
• GIS Valuation
• E-Stamp templates
• DM-P2 rate/guideline/CVC
Phase 3
08 Jun 2027
• Document Registration
• Encumbrance Search (EC)
• Verify · PoA · DRO/IGRO
• Document MIS / Dashboard
• Filings · corrections · memo
• DM-P3 books + EC indexes
Phase 4
14 Jul 2027
• Firm Registration (DRO)
• Firm MIS / Dashboard
• Firm audit views
• Reuse Phase 1 platform
• DM-P4 firm masters

## Slide 6
Master timeline & Go Live dates
17 Aug 2026 → 16 Jul 2027 (11 months)
Kaveri 3.0 Programme Plan v0.4 | PLAN-K3-PROG-001 | Confidential — Steering
6/14
Phase | Design | Build | Test | Go Live
1 — Marriage + Platform | 24-08 → 26-09 | 25-08 → 03-10 | 22-09 → 14-10 | 21-10-2026
2 — Calculators / Valuator | 22-09 → 28-11 | 22-10 → 30-01 | 05-01 → 28-02 | 16-03-2027
3 — Document + EC | 06-10 → 19-12 | 27-10 → 24-04 | 01-03 → 22-05 | 08-06-2027
4 — Firm Registration | 16-02 → 28-03 | 30-03 → 13-06 | 18-05 → 04-07 | 14-07-2027
Key milestones
Aug 17
T0 / BR start
Oct 15
BR window end
Oct 21
P1 LIVE
Mar 16
P2 LIVE
Jun 08
P3 LIVE
Jul 14
P4 LIVE

## Slide 7
Phase 1 deep-dive — Go Live 21 Oct 2026
All-hands · ~9 weeks · pathfinder
Kaveri 3.0 Programme Plan v0.4 | PLAN-K3-PROG-001 | Confidential — Steering
7/14
Must at cutover
Marriage Online (eSign) + Offline (DEO)
User Management (login, transfer, relieving)
eKYC · eSign · Khajane payment
Scanning spine · Marriage Dashboard & MIS
CC MVP (after 05-Oct discussion)
DM-P1 data cutover (freeze 15–20 Oct)
Build waves
W0 25-Aug–12-Sep: Platform + adapters
W1 08–26 Sep: Marriage Online path
W2 22-Sep–03-Oct: Offline + Scan + MIS
W3 06–14 Oct: CC MVP + UAT burn-down
Cutover 15–21 Oct: deploy + data + smoke
P1.1 to 15-Nov: Refund/Audit/MDM finish
SDLC stage | Window | Primary owners
BR (Marriage / User Mgmt first) | 17-08 → 15-10 | BA ×2, Domain, PO
HLD + Tech Architecture | 24-08 → 12-09 | Architect, Tech Leads
Development (all 8 Full Stack) | 25-08 → 03-10 | FS, Integration, DBA, UI/UX
Testing / UAT | 22-09 → 14-10 | QA, Test Eng, Perf/Sec
Deploy + Go Live | 15-10 → 21-10 | DevOps, Migration, Steering

## Slide 8
Phases 2–4 — summary
After Phase 1 capacity rebalance
Kaveri 3.0 Programme Plan v0.4 | PLAN-K3-PROG-001 | Confidential — Steering
8/14
Phase | Focus | Build start | Go Live | Migration
2 | Stamp/Guideline calculators, CVC, GIS, E-Stamp | 22-10-2026 | 16-03-2027 | DM-P2 rates & values
3 | Document Registration, EC, DRO/IGRO, MIS | 27-10-2026 | 08-06-2027 | DM-P3 books + EC (largest)
4 | Firm Registration (DRO) | 30-03-2027 | 14-07-2027 | DM-P4 firm data
Execution notes
• From 22 Oct: split squads — ~3–4 Full Stack on Phase 2; ~4–5 on Phase 3; Firm after P3 freeze
• Phase 2 may use shadow compare vs As-Is calculators before hard cutover
• Phase 3: pilot SRO(s) then statewide by Jun 2027; EC index pipeline starts Oct 2026
• Phase 4 reuses Identity, payment, eSign, scanning, audit from Phase 1
• Legal: Stamp Act 1957 + CVC Rules 2003 (P2); Registration Act 1908 + Rules 1965 + Act 47/2024 (P3)

## Slide 9
SDLC stages — every phase
Overlapping windows; gates before Go Live
Kaveri 3.0 Programme Plan v0.4 | PLAN-K3-PROG-001 | Confidential — Steering
9/14
1 Business Requirements
1
2 HLD
2
3 Technical Architecture
3
4 SDD
4
5 LLD
5
6 Software Development
6
7 Software Testing
7
8 Software Deployment
8
9 Go Live
9
10 Data Migration
10

## Slide 10
IT Cell resources — 39 posts
Source: K3_ITCellRequirement.pdf
Kaveri 3.0 Programme Plan v0.4 | PLAN-K3-PROG-001 | Confidential — Steering
10/14
Category | Roles | Posts
Leadership | PO, PM, Transition, Content, Security, DevOps | 6
Architecture / Tech | Technical Architect, Technology Lead ×2 | 3
BA / Domain | Business Analyst ×2, Domain Expert | 3
Engineering | Full Stack ×8, Integration, UI/UX, DBA, Migration | 12
Quality | QA ×2, Test Engineers ×4, Perf & Security Test Lead | 7
Analytics | BI & Analytics, AI/ML Specialist | 2
Support | L2 Support Engineers | 6
Total |  | 39
Capacity rule: All 8 Full Stack on Phase 1 until 21 Oct → then split P2 / P3 squads. Migration Specialist continuous from M1.
Primary bottleneck: Full Stack (8) and single Integration Engineer (Khajane → eSign → eKYC serialised).

## Slide 11
Data migration — Kaveri 1.0 / 2.0
Continuous workstream §5A · MIG-K3-PROG-001
Kaveri 3.0 Programme Plan v0.4 | PLAN-K3-PROG-001 | Confidential — Steering
11/14
In scope
Structured DB data from Kaveri 1.0 & 2.0
Users, offices, masters, fee/receipt keys
Marriage, Document, EC indexes, Firm
Already-stored scans/PDFs (re-link)
2.0 = primary cutover; 1.0 = historical fill
Approach
Discover → Map → ETL → Dry-run
Reconcile → UAT on migrated data
Freeze + Delta → Cutover → Hypercare
Idempotent pipelines + quarantine tables
Rollback: legacy read-only fallback window
Out of scope unless Steering promotes: paper digitisation backlog (#32), Accounts (#34), Mobile (#48)
Gate: No phase Go Live without signed Migration Exit Report (counts, samples, Domain + PO + Security).

## Slide 12
Migration packages by phase
DM-P1 … DM-P4 must complete before respective Go Live
Kaveri 3.0 Programme Plan v0.4 | PLAN-K3-PROG-001 | Confidential — Steering
12/14
Phase | Package IDs | Must migrate | Cutover
1 | DM-P1-01..06 | Masters, users, marriage, images, fee refs | 15–20 Oct 2026
2 | DM-P2-01..04 | Stamp rates, guideline, CVC, GIS keys | With 16-03-2027 GL
3 | DM-P3-01..07 | Regn books, pendency, EC indexes, deed links | With 08-06-2027 GL
4 | DM-P4-01..02 | Firm masters, certificates, open amendments | With 14-07-2027 GL
Near-term migration milestones
• 05 Sep 2026 — Source inventory & access pack complete (1.0 + 2.0)
• 20 Sep 2026 — Phase 1 field-mapping workbook frozen
• 05 Oct 2026 — Phase 1 ETL dry-run complete; UAT only on migrated data
• 20 Oct 2026 — DM-P1 Migration Exit Report signed
• Oct 2026 onward — Phase 3 EC index pipeline (largest volume) starts early

## Slide 13
Key risks & governance
Steering cadence: fortnightly in the 11-month window
Kaveri 3.0 Programme Plan v0.4 | PLAN-K3-PROG-001 | Confidential — Steering
13/14
ID | Risk | Mitigation
R-00 | Phase 1 only ~9 weeks to 21 Oct | All-hands FS; daily war-room; scope freeze
R-00b | P1 data migration incomplete | DM-P1 from 01-Sep; UAT on migrated data
R-01 | Only 8 Full Stack for 4 phases | Squad waves; no parallel greenfield
R-02 | Single Integration Engineer | Stub-first; Khajane→eSign→eKYC order
R-07 | EC/register migration volume | EC pipeline from Oct; pilot SRO parity
R-08 | Scope creep (mobile/paper/accounts) | Change board; equal swap-out
Go Live gate (every phase): RTM green · Legal lock · Migration Exit · Freeze/rollback · Security/Perf/DR · Training · Steering sign-off

## Slide 14
Decisions requested
Approve plan v0.4 to proceed
Kaveri 3.0 Programme Plan v0.4 | PLAN-K3-PROG-001 | Confidential — Steering
14/14
1. Approve Phase 1 Go Live target — 21 October 2026 (3rd week of October)
2. Approve 11-month programme end — all modules live by 14 July 2027 (≤ 16 July 2027)
3. Approve four-phase scope (Marriage platform → Calculators → Document/EC → Firm)
4. Approve Data Migration workstream from Kaveri 1.0/2.0 with mandatory exit reports
5. Confirm IT Cell 39-post roster as delivery capacity baseline
6. Authorise legacy write-freeze windows (Phase 1: 15–20 Oct 2026) via department circular
Source: Project_Plan_Kaveri_3.0_Programme_v0.4.md / .docx