## Revised Schedule
| Mode of Meeting | Online/ Offline
| Attendees | Committee members, AIGR Comp, Kaveri IT Cell, KPMU
Sr.No | Module | Discussion Topic | Owner | Duration (1 day: 8 hours) | Planned Date | Status | Parallel / Notes | Modules List Ref
1 | Marriage | Hindu Marriage (Current Issues) | DSR | 1 day | 17-08-2026 | Completed | Completed - Sr.1-7 one day (merged) | Completed - Sr.1-7 one day (merged)
2 | Marriage | Special Marriage (Current Issues) | DSR |  |  |  |  | Covered with Sr.1
3 | Marriage | Special Marriage Other Forms (Current Issues) | DSR |  |  |  |  | Covered with Sr.1
4 | Marriage | Business Re-Engineering (process improvements) | DSR |  |  |  |  | Covered with Sr.1
5 | Marriage | Reporting requirements | DSR |  |  |  |  | Covered with Sr.1
6 | Marriage | Data Integration with other department (post registration) | DSR |  |  |  |  | Covered with Sr.1
7 | Marriage | Dashboard Requirements | DSR |  |  |  |  | Covered with Sr.1
8 | Marriage | Audit Requirements | DSR | 1 day | 18-08-2026 | Completed | Completed | Completed
9 | Marriage | Business Requirement Document (BRD) | BA | 3 days | 19-08-2026 to 21-08-2026 | In Progress | BA track / In Progress | BA track / In Progress
10 | User Management | User management, login, transfer, relieving requirements | DSR, BA | 1 day | 24-08-2026 |  | After 21-08; 22-08 is 4th Saturday holiday | Modules list #47
11 | User Management BRD | Business Requirement Document (BRD) | BA | 1 day | 25-08-2026 |  | BA parallel with Sr.12 | BA parallel with Document start
12 | Document | Registration core: Registration, Appointment, Status tracking (Current issues & process walkthrough) | DSR | 2 days | 25-08-2026 to 27-08-2026 |  |  | Sub-modules #1, #2, #19
13 | Document | Stamp duty and Registration fee calculation; Guideline value calculation | DSR | 2 days | 28-08-2026 to 29-08-2026 |  |  | Sub-modules #4, #5
14 | Document | Valuation Module (CVC) and GIS valuation | DSR | 2 days | 31-08-2026 to 01-09-2026 |  |  | Sub-modules #21, #22
15 | Document | Rule 17(2) filing, Rule 17(3) filing, and Old pending release module | DSR | 2 days | 02-09-2026 to 03-09-2026 |  |  | Sub-modules #6, #7, #8
16 | Document | Filing documents (FRUITS Part 3a, 6), Scanning, Memo transmission and filing | DSR | 2 days | 04-09-2026 to 05-09-2026 |  |  | Sub-modules #11, #12, #13
17 | Document | Re-Registration module and Will after Death of testator | DSR | 1 day | 07-09-2026 |  |  | Sub-modules #9/#23, #10
18 | Document | 68(2) correction and Cross-reference Rule 123 | DSR | 1 day | 08-09-2026 |  |  | Sub-modules #14, #15
19 | Document | Integration module, Integration exemption, Court entry, and Liability | DSR | 2 days | 09-09-2026 to 10-09-2026 |  |  | Sub-modules #3, #16, #17, #18
20 | Document | Investigation and Search; Verify Document | DSR | 1 day | 11-09-2026 |  |  | Sub-modules #20, #26
21 | Document | Power of Attorney Authentication Module | DSR | 1 day | 15-09-2026 |  |  | Sub-module #27
22 | Document | DRO processes: Undervaluation, Deposit of will, Adjudication of documents | DSR | 2 days | 16-09-2026 to 17-09-2026 |  |  | Sub-modules #42, #43, #44 (DRO)
23 | Document | IGRO: Appeal (property valuation appeals and related IGR processes) | DSR | 1 day | 18-09-2026 |  |  | Sub-module #45 (IGRO)
24 | Document | Current issues, Business Re-Engineering, MIS Reports (Statutory/Statistical/Integration/Reconciliation), Dashboard (SR/DR/IGR) | DSR | 2 days | 19-09-2026 to 21-09-2026 |  |  | Cross-cutting + MIS #35-40
25 | Digital E-Stamp | E-Stamping / Digital E-Stamp: template design for all types of documents | DSR | 8 days | 22-09-2026 to 01-10-2026 |  | Parallel with Sr.28 (BA BRD) | Modules list #50; parallel with Document BRD
26 | Encumbrance Search | EC - Current issues (Functional) and Process Improvements | DSR | 1 day | 03-10-2026 |  | Parallel with Sr.28 (BA BRD) | Modules list #24
27 | Certified Copies | CC - Current issues (Functional) and Process Improvements | DSR | 1 day | 05-10-2026 |  | Parallel with Sr.28; skips 02-10 Gandhi Jayanti if applicable | Modules list #25
28 | Document, EC, CC, Verify, PoA BRD | Business Requirement Document (BRD) for Document Registration sub-modules, EC, CC, Verify Document, PoA Authentication | BA | 12 days | 19-09-2026 to 05-10-2026 |  | Starts after Document Registration discussions through Sr.23; parallel with Sr.25-29 | Starts after Sr.23 (IGRO); parallel with E-Stamp/EC/CC/Firm
29 | Firm | Firm Registration - Current Issues | DSR | 2 days | 06-10-2026 to 07-10-2026 |  | Parallel with closing of Sr.28 where dates overlap | Modules list #41 (DRO)
30 | Firm | Business Re-Engineering (process improvements), MIS Reports, Dashboard, Auditing Requirements | DSR | 2 days | 08-10-2026 to 09-10-2026
31 | Firm | Business Requirement Document (BRD) | BA | 3 days | 12-10-2026 to 14-10-2026 |  | After Sr.30; parallel with Sr.32-34 | After Firm discussions; parallel with Refund/Audit/MDM
32 | Refund | Refund process capturing | DSR | 1 day | 12-10-2026 |  | Parallel with Sr.31 | Modules list #28
33 | Audit | Audit module Requirements | DSR | 1 day | 13-10-2026 |  | Parallel with Sr.31 | Modules list #33
34 | Master Data Management | Kaveri Master Data Management | DSR | 1 day | 14-10-2026 |  | Parallel with Sr.31 | Modules list #46
35 | Refund, Audit, Master Data Management - BRD | Business Requirement Document (BRD) | BA | 1 day | 15-10-2026 |  | After Sr.32-34; 60-day window end target 15-10-2026 | After Sr.32-34; within 60-day window

## Planning Notes
Kaveri 3.0 - Requirements Discussion Schedule (v3)
Document topics aligned to Kaveri_2.0_Moduleslist.xlsx sub-modules
Planning window
Start: 17-08-2026 ¦ 60 calendar days end: 15-10-2026 ¦ Scheduled finish: 15-10-2026
Source modules: Requirement Discussions/Modules/DocumentRegistration/Kaveri_2.0_Moduleslist.xlsx
Scheduling rules
- Exclude Sundays, 2nd and 4th Saturdays, and GoK gazetted holidays (GovernmentOfKarnatakaHolidayList.docx).
- 1st, 3rd and 5th Saturdays are working days.
- Parallel BA BRD drafting overlaps DSR discussion sessions where owners differ.
Document sub-module mapping
Document discussion topics mapped from Kaveri_2.0_Moduleslist.xlsx:
Sr.12 <- #1 Registration, #2 Appointment, #19 Status tracking
Sr.13 <- #4 Stamp duty and Registration fee calculation, #5 Guideline value calculation
Sr.14 <- #21 Valuation Module (CVC), #22 GIS valuation
Sr.15 <- #6 Rule 17(2), #7 Rule 17(3), #8 Old pending release
Sr.16 <- #11 Filing documents (FRUITS Part 3a, 6), #12 Scanning, #13 Memo transmission and filing
Sr.17 <- #9/#23 Re-Registration, #10 Will after Death of testator
Sr.18 <- #14 68(2) correction, #15 Cross-reference Rule 123
Sr.19 <- #3 Integration module, #16 Integration exemption, #17 Court entry, #18 Liability
Sr.20 <- #20 Investigation and Search, #26 Verify Document
Sr.21 <- #27 Power of Attorney Authentication Module
Sr.22 <- #42 Undervaluation, #43 Deposit of will, #44 Adjudication of documents (DRO)
Sr.23 <- #45 Appeal (IGRO)
Sr.24 <- Cross-cutting Current issues / BRE / MIS #35-40 / Dashboard
Sr.25 <- #50 E-Stamping (separate module row)
Sr.26 <- #24 EC
Sr.27 <- #25 CC
Non-working days in schedule period (excl. ordinary Sundays)
22-08-2026 - Saturday - 4th Saturday (Govt. holiday)
26-08-2026 - Wednesday - Eid-e-Milad
12-09-2026 - Saturday - 2nd Saturday (Govt. holiday)
14-09-2026 - Monday - Varasiddhi Vinayaka Vrata
26-09-2026 - Saturday - 4th Saturday (Govt. holiday)
02-10-2026 - Friday - Mahatma Gandhi Jayanti
10-10-2026 - Saturday - 2nd Saturday (Govt. holiday)
Planned dates
Sr.1-7: 17-08-2026
Sr.8: 18-08-2026
Sr.9: 19-08-2026 to 21-08-2026
Sr.10: 24-08-2026
Sr.11: 25-08-2026
Sr.12: 25-08-2026 to 27-08-2026
Sr.13: 28-08-2026 to 29-08-2026
Sr.14: 31-08-2026 to 01-09-2026
Sr.15: 02-09-2026 to 03-09-2026
Sr.16: 04-09-2026 to 05-09-2026
Sr.17: 07-09-2026
Sr.18: 08-09-2026
Sr.19: 09-09-2026 to 10-09-2026
Sr.20: 11-09-2026
Sr.21: 15-09-2026
Sr.22: 16-09-2026 to 17-09-2026
Sr.23: 18-09-2026
Sr.24: 19-09-2026 to 21-09-2026
Sr.25: 22-09-2026 to 01-10-2026
Sr.26: 03-10-2026
Sr.27: 05-10-2026
Sr.28: 19-09-2026 to 05-10-2026
Sr.29: 06-10-2026 to 07-10-2026
Sr.30: 08-10-2026 to 09-10-2026
Sr.31: 12-10-2026 to 14-10-2026
Sr.32: 12-10-2026
Sr.33: 13-10-2026
Sr.34: 14-10-2026
Sr.35: 15-10-2026

## Document Sub-Modules Ref
Modules Number | Main Module | Sub Modules | Scheduled under Sr.No
1 | Registration | Registration | 12
2 | Registration | Appointment | 12
3 | Registration | Integration module | 19
4 | Registration | Stamp duty and Registration fee calculation | 13
5 | Registration | Guideline value calculation | 13
6 | Registration | Rule 17 (2) filing | 15
7 | Registration | Rule 17 (3) filing | 15
8 | Registration | Old pending relesae module | 15
9 | Registration | Re Registration module | 17
10 | Registration | Will after Death of testator | 17
11 | Registration | Filing documents (FRUITS), Part 3a, 6 | 16
12 | Registration | Scanning | 16
13 | Registration | Memo trasnmission and filing | 16
14 | Registration | 68(2) correction | 18
15 | Registration | Cross-reference Rule 123 | 18
16 | Registration | Integration exemption | 19
17 | Registration | Court entry | 19
18 | Registration | Liabality | 19
19 | Registration | Status tracking | 12
20 | Registration | Investigation and Search | 20
21 | Registration | Valuation Module (CVC) | 14
22 | Registration | GIS valuation | 14
23 | Registration | Re-Registration | 17
24 | EC | EC | 26
25 | CC | CC | 27
26 | Verify Document | Verify Document | 20
27 | Power of attorney Authentication Module | Power of attorney Authentication Module | 21
28 | Refund Module | Refund Module | 32
29 | Marriage | Hindu Marriage | 1
30 | Marriage | Special Marriage | 2
31 | Marriage | Special Marriage in Other forms | 3
32 | Leagacy record digitisation | Leagacy record digitisation | Not in this schedule iteration
33 | Audit | Audit | 33
34 | Accounts | Accounts | Not in this schedule iteration
35 | MIS | Staturory (44) | 24
36 | MIS | Satitisical (54) | 24
37 | MIS | Integration (15) | 24
38 | MIS | Computer realted (4) | 24
39 | MIS | Reconcilation (5) | 24
40 | MIS | HR (5) | 24
41 | DRO | Firm Registration | 29
42 | DRO | Undervaluation | 22
43 | DRO | Deposit of will | 22
44 | DRO | Adjudication of documents | 22
45 | IGRO | Appeal | 23
46 | Master Data Management | Master Data Management | 34
47 | User Managment | User Managment | 10
48 | Mobile application | Mobile application | Not in this schedule iteration
49 | Training Module | Master Trainer, Training Plan | Not in this schedule iteration
50 | E-Stamping | E-Stamping | 25