## Sheet1
Marriage Registration Module - Effort Estimation (in Days)
S.No | Module / Task | Effort (Days) | Notes
1 | Marriage Details Entry | 6
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 1
iv | Testing (T) | 1
2 | Bride / Bridegroom Details | 6
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 1
iv | Testing (T) | 1
3 | e-KYC Integration - Bride / Groom / Witness | 6
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 1
iv | Testing (T) | 1
4 | Witness Entry | 6
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 1
iv | Testing (T) | 1
5 | Supporting Document Upload | 6
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 1
iv | Testing (T) | 1
6 | Review Summary | 6
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 1
iv | Testing (T) | 1
7 | Appointment Scheduling | 6
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 1
iv | Testing (T) | 1
8 | Sub-Registrar Scrutiny | 6
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 1
iv | Testing (T) | 1
9 | Payment Service | 6
i | API | 3
ii | UI | 1
iii | Code Review (CR) | 1
iv | Testing (T) | 1
10 | Integration with Payment Service | 6
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 1
iv | Testing (T) | 1
11 | e-KYC / Face Authentication Service | 8
i | API | 3
ii | UI | 1
iii | Code Review (CR) | 2
iv | Testing (T) | 2
12 | Workflow - Marriage Registration | 9
i | API | 3
ii | UI | 2
iii | Code Review (CR) | 2
iv | Testing (T) | 2
13 | FOA / DBO Screen | 6
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 1
iv | Testing (T) | 1
14 | SRO Registration & DSC Screen | 6
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 1
iv | Testing (T) | 1
15 | DSC Microservice | 7
i | API | 3
ii | UI | 1
iii | Code Review (CR) | 2
iv | Testing (T) | 1
16 | Objection Entry Screen | 8
i | API | 3
ii | UI | 2
iii | Code Review (CR) | 1
iv | Testing (T) | 2
17 | Generating Summons for Objection | 6
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 1
iv | Testing (T) | 1
18 | DSC / Uploading Enquiry Order | 6
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 1
iv | Testing (T) | 1
19 | Generate Certificate (HM / SM / PM) | 6
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 1
iv | Testing (T) | 1
20 | Intended Notice Certificate | 6
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 1
iv | Testing (T) | 1
21 | Form II, IA, IIA Generation | 8
i | API | 4
ii | UI | 2
iii | Code Review (CR) | 1
iv | Testing (T) | 1
22 | Integrating with e-Sign Microservice | 6 | In original notes, this replaced a crossed-out 'e-Sign Service/Microservice' entry - please confirm
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 1
iv | Testing (T) | 1
23 | Dashboard - Marriage | 7
i | API | 3
ii | UI | 2
iii | Code Review (CR) | 1
iv | Testing (T) | 1
24 | MIS Reports | 7
i | API | 3
ii | UI | 2
iii | Code Review (CR) | 1
iv | Testing (T) | 1
25 | Null & Void Endorsement Entry | 6
i | API | 2
ii | UI | 2
iii | Code Review (CR) | 1
iv | Testing (T) | 1
26 | Hindu Marriage - Online / Offline Flow Registration | 11
i | API | 3
ii | UI | 3
iii | Code Review (CR) | 3
iv | Testing (T) | 2
27 | Special Marriage Notice - Online / Offline Workflow | 11
i | API | 3
ii | UI | 3
iii | Code Review (CR) | 3
iv | Testing (T) | 2
28 | Special Marriage Registration (Online / Offline) | 11
i | API | 3
ii | UI | 3
iii | Code Review (CR) | 3
iv | Testing (T) | 2
29 | Parsi Marriage - Online / Offline | 11
i | API | 3
ii | UI | 3
iii | Code Review (CR) | 3
iv | Testing (T) | 2
GRAND TOTAL (All Tasks) |  | 206